## Sheet 1
DKN AW26 DROP 2 (W26-1) WOMEN'S NOSORDER CIRCULAR KNIT PRODUCTION STATUS REPORT | [30 empty] | Report Generated Date: 29/01/2026 12:03
S.No | Buyer | Factory | Customer Season | CT Season | Style No | Image | Style Description | Fabric Quality | Treatment | Buyer Po No | Color | Quantity |  | Original order received Dt | Etd Ex factory as per P.O | Factory Confirmed Dt | Trims Inhouse |  | Fabric Inhouse |  | PPS Submission |  |  | Cut Qty | Sewing Start |  | Sewing End |  | Sewing Qty | Inspection |  | Ex Factory Shipment |  |  | Shipped Qty | Balance Qty | Fabric Quality Mock up | Shipment samples | Remarks
[12 empty] | Col | Qty |  |  |  | Planned | Actual | Planned | Actual | Planned | Actual | PPS Approved |  | Planned | Actual | Planned | Actual |  | Planned | Actual | Planned | Actual | Extended |  |  | Approval | Approval
1 | DRYKORN MODEVERTRIEBS GMBH & CO | ELEVAR FASHION | AW 2026 DROP 2 | W26-1 | 890162 TAVIRA_2 522148 | #VALUE! | CIRCULAR KNIT WOMENS TANK TOP | 2X2 RIB/100% COTTON/34S////18GG/260//YARN DYED | YARN DYED + PANEL WASH | 131673 | 6602 | 500 | 500 | 27-MAR-2026 | 10-JUN-2026 | 30-APR-2026 | 29-APR-2026 |  | 29-APR-2026 |  | 05-MAY-2026 |  |  |  | 23-MAY-2026 |  | 05-JUN-2026 |  |  | 09-JUN-2026 |  | 10-JUN-2026 |  |  |  | -500
2 | DRYKORN MODEVERTRIEBS GMBH & CO | ELEVAR FASHION | AW 2026 DROP 2 | W26-1 | 89871 KOALE 522148 | #VALUE! | CIRCULAR KNIT WOMENS T-SHIRT HALF SLEEVE ROUND NECK | 2X2 RIB/100% COTTON/34S////18GG/260//YARN DYED | FIBRE DYED MELANGE + PANEL BIO WASH | 131675 | 6602 | 500 | 500 | 27-MAR-2026 | 10-JUN-2026 | 30-APR-2026 | 29-APR-2026 |  | 29-APR-2026 |  | 05-MAY-2026 |  |  |  | 23-MAY-2026 |  | 05-JUN-2026 |  |  | 09-JUN-2026 |  | 10-JUN-2026 |  |  |  | -500
3 | DRYKORN MODEVERTRIEBS GMBH & CO | ELEVAR FASHION | AW 2026 DROP 2 | W26-1 | 89556 OLINA 522148 | #VALUE! | CIRCULAR KNIT WOMENS TANK TOP | 2X2 RIB/100% COTTON/34S////18GG/260//YARN DYED | FIBRE DYED MELANGE + PANEL BIO WASH | 131673 | 6602 | 500 | 500 | 27-MAR-2026 | 10-JUN-2026 | 30-APR-2026 | 29-APR-2026 |  | 29-APR-2026 |  | 05-MAY-2026 |  |  |  | 23-MAY-2026 |  | 05-JUN-2026 |  |  | 09-JUN-2026 |  | 10-JUN-2026 |  |  |  | -500
Grand Total | [12 empty] | 1500 | [10 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 | -1500