## Sheet 1
Marc O' Polo Denim Girls FW26 (1) MA08 MA09 Order status report- Bulk Production | [36 empty] | 2026-02-13
S.No | Buyer | Factory | Customer Season | Style No | 2026-03-15 | Image | Style Description | Fabric Quality | Treatment | Buyer Po No | Color | Quantity |  | Original order received Dt | Etd Ex factory as per P.O | Factory Confirmed Dt | Trims Inhouse |  | Fabric Inhouse |  | Sizeset Submission |  |  | Cut Qty | Sewing Start |  | Sewing End |  | Sewing Qty | Inspection |  | Ex Factory Shipment |  |  | Shipped Qty | Balance Qty | Remarks
[12 empty] | Col | Qty |  |  |  | Planned | Actual | Planned | Actual | Planned | Actual | Approved |  | Planned | Actual | Planned | Actual |  | Planned | Actual | Planned | Actual | Extended
1 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | DWJE FW26 08 1000000158 5000007952 | 3000000347 | #VALUE! | CIRCULAR KNIT WOMENS SWEAT SHIRT | DIAGONAL FRENCH TERRY/100% ORGANIC COTTON/34S/260/YARN DYED + PANEL WASH | YARN DYED + PANEL WASH | 7000018563, 7000018595, 7000018647 | 0093-BLACK MULTI 01 | 2176 | 2176 | 12-FEB-2026 | 09-MAY-2026 | 22-APR-2026 | 22-MAR-2026 | 2026-03-15 | 30/3-7/4 | 2026-04-01 | 2026-04-05 | 2026-04-09 | 2026-04-09 | 2379 | 2026-04-10 | 2026-04-17 | 2026-04-21 |  |  | 2026-04-22 |  | 2026-04-22 |  |  |  | -2176 | Bulk u/ sewing. Ontime
2 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | DWJE FW26 08 1000001702 5000012167 | 3000005050 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | 2X2 RIB LYCRA/96% ORGANIC COTTON 4% ELASTHANE/50S/40D///28GG/180/34D/FABRIC DYED + AOP | ALL OVER PRINT+ PANEL WASHED | 7000018537, 7000018567, 7000018601, 7000018604, 7000018659 | 7026 DARK RED MULTI 01 | 1750 | 2902 | 13-FEB-2026 | 12-MAY-2026 | 22-APR-2026 | 24-MAR-2026 | 2026-03-15 | 2026-03-25 | 2026-03-23 | 2026-03-30 | 2026-04-02 | 2026-04-02 | 1914 | 2026-04-16 | 2026-04-14 | 2026-04-20 |  |  | 2026-04-22 |  | 2026-04-15 |  |  |  | -1750 | Bulk u/ sewing. Ontime
[11 empty] | 9066 LIGHT YELLOW MULTI 01 | 1152 | [11 empty] | 1266 |  |  |  | 2026-04-16 | 1266 | [6 empty] | -1152
3 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | DWJE FW26 08 1000000099 5000007907 | 3000000459 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | 4X3 RIB/96% ORGANIC COTTON 4% ELASTHANE/34S/230/FABRIC DYED + PANEL WASHED | FABRIC DYE + PANEL WASH | 7000018534, 7000018561, 7000018588, 7000018592, 7000018642 | 6937-MAHAGONY JAM | 1527 | 3724 | 12-FEB-2026 | 12-MAY-2026 | 22-APR-2026 | 24-MAR-2026 | 2026-03-15 | 2026-03-27 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 1750 | 2026-03-27 | 2026-03-27 | 2026-04-15 | 2026-04-13 | 1741 | 2026-04-20 |  | 2026-04-15 |  |  |  | -1527 | Bulk u/ ironing+ packing.
[11 empty] | 0361-LIGHT GRAPHITE | 1596 | [7 empty] | 2026-03-16 |  |  |  | 1676 |  |  |  |  | 1665 | [6 empty] | -1596
[11 empty] | 4820 - LAKE BLUE | 601 | [7 empty] | 2026-03-15 |  |  |  | 682 |  |  |  |  | 682 | [6 empty] | -601
4 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | DWJE FW26 08 1000000052 5000011502 | 3000000763 | #VALUE! | CIRCULAR KNIT WOMENS SWEAT SHIRT | DIAGONAL FRENCH TERRY/100% ORGANIC COTTON/34S/260/FABRIC DYED + PANEL WASHED | FABRIC DYE + PANEL WASH | 7000018535, 7000018564, 7000018596, 7000018648 | 1348- ESPRESSO BROWN | 2281 | 9455 | 12-FEB-2026 | 12-MAY-2026 | 22-APR-2026 | 24-MAR-2026 | 2026-03-15 | 24-MAR-2026 | 2026-03-15 | 31-MAR-2026 | 2026-03-13 | 2026-03-13 | 2493 | 2026-03-30 | 2026-03-27 | 2026-04-22 |  | 2493 | 2026-04-24 | 2026-04-17 | 2026-04-24 |  |  |  | -2281 | Bulk u/ ironing+ packing.
[11 empty] | 6913- DEEP BURGANDY | 1239 | [7 empty] | 2026-03-12 |  |  |  | 1361 |  |  |  |  | 1361 |  | 2026-04-22 |  |  |  |  | -1239
[11 empty] | 6322- SMOKY GRAPE | 1305 | [7 empty] | 2026-03-15 |  |  |  | 1434 |  |  |  |  | 1434 |  | 2026-04-20 |  |  |  |  | -1305
[11 empty] | 8989- BUTTER YELLOW | 1416 | [7 empty] | 2026-03-20 |  |  |  | 1550 | [6 empty] | 2026-04-24 |  |  |  |  | -1416
[11 empty] | 6937- MAHAGONY JAM | 1584 | [7 empty] | 2026-03-12 |  |  |  | 1733 |  |  |  |  | 1733 |  | 2026-04-22 |  |  |  |  | -1584
[11 empty] | 4779- FALL SKY | 828 | [7 empty] | 2026-03-11 |  |  |  | 931 |  |  |  |  | 931 |  | 2026-04-22 |  |  |  |  | -828
[11 empty] | 4820- LAKE BLUE | 802 | [7 empty] | 2026-03-20 |  |  |  | 902 | [6 empty] | 2026-04-24 |  |  |  |  | -802
5 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | DWJE FW26 08 1000000826 5000012387 | 3000005199 | #VALUE! | CIRCULAR KNIT WOMENS SWEAT SHIRT | FRENCH TERRY/100% ORGANIC COTTON/30S/30S/10S//20GG/360/34D/FABRIC DYED + PEACHED + BRUSHED + PANEL WASH | FABRIC LAVA DYED + ACID WASH | 7000018570, 7000018614, 7000018617, 7000018674 | 6937- MAHAGONY JAM | 1291 | 1999 | 13-FEB-2026 | 12-MAY-2026 | 22-APR-2026 | 24-MAR-2026 | 2026-03-15 | 24-MAR-2026 | 2026-04-05 | 2026-04-04 | 2026-04-06 | 2026-04-06 | 1420 | 2026-04-12 | 2026-04-15 | 2026-04-22 |  |  | 2026-04-24 |  | 2026-04-14 |  |  |  | -1291 | Bulk u/ ironing+ packing.
[11 empty] | 8989- BUTTER YELLOW | 708 | [7 empty] | 2026-03-25 |  |  |  | 804 | [11 empty] | -708
6 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | DWJE FW26 08 1000000826 5000014733 | 3000006775 | #VALUE! | CIRCULAR KNIT WOMENS SWEAT JACKET | FRENCH TERRY/100% ORGANIC COTTON/30S/30S/10S//20GG/360/34D/FABRIC DYED + PEACHED + BRUSHED + PANEL WASH | FABRIC LAVA DYED + ACID WASH + PEACHED | 7000018577, 7000018631, 7000018634, 7000018688 | 0361-LIGHT GRAPHITE | 466 | 1062 | 13-FEB-2026 | 12-MAY-2026 | 22-APR-2026 | 24-MAR-2026 | 2026-03-30 | 24-MAR-2026 | 2026-03-27 | 2026-04-24 |  |  |  | 2026-04-15 |  | 2026-04-20 |  |  | 2026-04-22 |  | 2026-04-20 |  |  |  | -466 | Sizeset rejected. Reoffer-24/4; Await revise line plan
[11 empty] | 6937- MAHAGONY JAM | 596 | [7 empty] | 2026-03-30 | [15 empty] | -596
7 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | DWJE FW26 08 1000000260 5000012316 | 3000005161 | #VALUE! | CIRCULAR KNIT WOMENS SWEAT SHIRT | FRENCH TERRY/100% ORGANIC COTTON/30S/30S/10S//20GG/360/30D/RFD + PEACHED +BRUSHED | FABRIC LAVA DYED + ACID WASH | 7000018538, 7000018568, 7000018606, 7000018608, 7000018664 | 6937- MAHAGONY JAM | 538 | 1770 | 2026-02-13 | 2026-05-12 | 22-APR-2026 | 24-MAR-2026 | 2026-03-15 | 24-MAR-2026 | 2026-03-12 | 31-MAR-2026 | 2026-03-19 | 2026-03-19 | 637 | 2026-04-02 | 2026-03-30 | 2026-04-07 | 2026-04-07 | 637 | 2026-04-22 |  | 2026-04-15 |  |  |  | -538 | Bulk u/ checking and ironing
[11 empty] | 8980- PARIS YELLOW | 526 | [11 empty] | 624 |  |  |  |  | 624 | [6 empty] | -526
[11 empty] | 0361-LIGHT GRAPHITE | 706 | [11 empty] | 834 |  |  |  |  | 834 | [6 empty] | -706
8 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | DWJE FW26 08 1000000772 5000007068 | 3000001601 | #VALUE! | CIRCULAR KNIT WOMENS T-SHIRT LONG SLEEVE ROUND NECK | 4X2 RIB/100% ORGANIC COTTON/34S////18GG/240//FABRIC DYED + PANEL WASHED | FABRIC DYE + PANEL WASH | 7000018533, 7000018560, 7000018640 | 1358- BURNISHED LOGS | 954 | 2970 | 2026-02-13 | 2026-05-12 | 22-APR-2026 | 24-MAR-2026 | 2026-03-12 | 24-MAR-2026 | 2026-03-28 | 31-MAR-2026 | 2026-03-30 | 2026-04-03 |  | 2026-04-13 |  | 2026-04-16 |  |  | 2026-04-20 |  | 2026-04-18 |  |  |  | -954 | U/ Cutting. Await revised plan
[11 empty] | 1183-SILKY WHITE | 1054 | [7 empty] | 2026-03-25 | [15 empty] | -1054
[11 empty] | 1348- ESPRESSO BROWN | 962 | [7 empty] | 2026-03-29 | [15 empty] | -962
9 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | DWJE FW26 08 1000000787 5000012326 | 3000005170 | #VALUE! | CIRCULAR KNIT WOMENS SWEAT SHIRT | POLAR FLEECE/100% RECYLED POLYESTER/75D/150D///22GG/420//FABRIC DYED | FABRIC DYED | 7000018611, 7000018670, 7000018569 | 0361-LIGHT GRAPHITE | 338 | 821 | 13-FEB-2026 | 2026-05-12 | 2026-05-05 | 2026-03-20 | 2026-03-20 | 2026-04-13 |  | 2026-04-15 |  |  |  | 2026-04-27 |  | 2026-05-02 |  |  | 2026-05-06 |  | 2026-05-06 |  |  |  | -338 | Await fabric to get i/h for planning
[11 empty] | 1171 – WHITE BLUSH | 483 | [23 empty] | -483
10 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | DWJE FW26 08 1000000787 5000012011 | 3000004937 | #VALUE! | CIRCULAR KNIT WOMENS SWEAT JACKET | POLAR FLEECE/100% RECYLED POLYESTER/75D/150D///22GG/420//FABRIC DYED | FABRIC DYED | 7000018598, 7000018656 | 1171 – WHITE BLUSH | 391 | 392 | 13-FEB-2026 | 2026-05-12 | 2026-05-05 | 20/3 -15/4 |  | 2026-04-13 |  | 2026-04-15 |  |  |  | 2026-04-21 |  | 2026-04-25 |  |  | 2026-04-30 |  | 2026-04-30 |  |  |  | -391 | Await fabric to get i/h for planning
[11 empty] | 6937- MAHAGONY JAM | 1 | [23 empty] | -1
11 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | DWJE FW26 08 1000000787 5000014558 | 3000006697 | #VALUE! | CIRCULAR KNIT WOMENS SWEAT JACKET | POLAR FLEECE/100% RECYLED POLYESTER/75D/150D///22GG/420//FABRIC DYED | FABRIC DYED | 7000018630, 7000018626, 7000018687, 7000018576 | 0361-LIGHT GRAPHITE | 864 | 3318 | 13-FEB-2026 | 2026-05-12 | 2026-05-05 | 20/3-15/4 |  | 2026-04-13 |  | 2026-04-15 |  |  |  | 2026-05-04 |  | 2026-05-18 |  |  | 2026-05-20 |  | 2026-05-20 |  |  |  | -864 | Await fabric to get i/h for planning
[11 empty] | 1171 – WHITE BLUSH | 798 | [23 empty] | -798
[11 empty] | 6937- MAHAGONY JAM | 1656 | [23 empty] | -1656
12 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA09 | DWJE FW26 09 1000000772 5000007068 | 3000001601 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | 4X2 RIB/100% ORGANIC COTTON/34S////18GG/240//FABRIC DYED + PANEL WASHED | FABRIC DYE + PANEL WASH | 7000018532, 7000018559, 7000018586, 7000018637 | 0001-BLACK | 1213 | 2756 | 13-FEB-2026 | 19-JUN-2026 | 29-MAY-2026 | 10-APR-2026 | 2026-03-12 | 10-APR-2026 | 4/4-8/4 | 20-APR-2026 |  |  |  | 2026-04-21 |  | 2026-04-25 |  |  | 2026-04-27 |  | 2026-04-27 |  |  |  | -1213 | Same line plan
[11 empty] | 6937-MAHAGONY JAM | 837 | [23 empty] | -837
[11 empty] | 8989- BUTTER YELLOW | 706 | [23 empty] | -706
13 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | DWJE FW26 08 1000000787 5000012326 | 3000005170 | #VALUE! | CIRCULAR KNIT WOMENS SWEAT SHIRT | POLAR FLEECE/100% RECYLED POLYESTER/75D/150D///22GG/420//FABRIC DYED | FABRIC DYED | 7000018539, 7000018611 | 0361-LIGHT GRAPHITE | 286 | 403 | 13-FEB-2026 | 19-JUN-2026 | 2026-05-27 | 2026-03-20 | 2026-03-20 | 2026-04-10 |  | 2026-05-15 |  |  |  | 2026-04-15 |  | 2026-04-21 |  |  | 2026-04-24 |  | 2026-04-24 |  |  |  | -286 | Await fabric to get i/h for planning
[11 empty] | 1171 – WHITE BLUSH | 117 | [23 empty] | -117
14 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | DWJE FW26 08 1000000787 5000012011 | 3000004937 | #VALUE! | CIRCULAR KNIT WOMENS SWEAT JACKET | POLAR FLEECE/100% RECYLED POLYESTER/75D/150D///22GG/420//FABRIC DYED | FABRIC DYED | 7000018536, 7000018566, 7000018598, | 1171 – WHITE BLUSH | 109 | 617 | 13-FEB-2026 | 19-JUN-2026 | 2026-05-27 | 20/3 -15/4 |  | 2026-04-25 | [5 empty] | 2026-05-11 |  | 2026-05-15 |  |  | 2026-05-21 |  | 2026-05-21 |  |  |  | -109 | Await fabric to get i/h for planning
[11 empty] | 6937- MAHAGONY JAM | 508 | [23 empty] | -508
15 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | DWJE FW26 08 1000000787 5000014558 | 3000006697 | #VALUE! | CIRCULAR KNIT WOMENS SWEAT JACKET | POLAR FLEECE/100% RECYLED POLYESTER/75D/150D///22GG/420//FABRIC DYED | FABRIC DYED | 7000018547 | 0361-LIGHT GRAPHITE | 287 | 1016 | 13-FEB-2026 | 19-JUN-2026 | 2026-05-27 | 20/3-15/4 |  | 10-APR-2026 | [5 empty] | 2026-04-20 |  | 2026-05-02 |  |  | 2026-05-07 |  | 2026-05-07 |  |  |  | -287 | Await fabric to get i/h for planning
[11 empty] | 1171 – WHITE BLUSH | 220 | [23 empty] | -220
[11 empty] | 6937- MAHAGONY JAM | 509 | [23 empty] | -509
35381

## Sheet1
Photo samples:8/4- 1st collection
Photo samples:30/4- Teddy fleece
PSS- 52:10/4
PSS -787:30/4