## Sheet 1
Marc O'Polo Denim Girls W26(1) NOS order status - Bulk Production | [36 empty] | 2026-03-04
S.No | Buyer | Factory | Customer Season | Style No | Style Name | Image | Style Description | Fabric Quality | Treatment | Buyer Po No | Color | Quantity |  | Original order received Dt | Etd Ex factory as per P.O | Factory Confirmed Dt | Trims Inhouse |  | Fabric Inhouse |  | Sizeset Submission |  |  | Cut Qty | Sewing Start |  | Sewing End |  | Sewing Qty | Inspection |  | Ex Factory Shipment |  |  | Shipped Qty | Balance Qty | Remarks
[12 empty] | Col | Qty |  |  |  | Planned | Actual | Planned | Actual | Planned | Actual | Approved |  | Planned | Actual | Planned | Actual |  | Planned | Actual | Planned | Actual | Extended
1 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MANOS08 | DWJE MANOS 08 1000000052 5000006286 | 3000000763 | #VALUE! | CIRCULAR KNIT WOMEN'S SWEAT SHIRT | DIAGONAL FRENCH TERRY/100% ORGANIC COTTON/34S/260/ FABRIC DYED + PANEL WASHED | FABRIC DYE + PANEL WASH | 7000022459 | 4139–NAVY TEAL | 1420 | 1420 | 04-MAR-2026 | 19-MAY-2026 | 05-MAY-2026 | 2026-03-25 | 2026-03-25 | 2026-03-20 | 2026-03-22 | 2026-03-23 | 2026-03-27 | 2026-03-27 | 1554 | 2026-04-23 |  | 2026-04-27 |  |  | 2026-04-30 | [5 empty] | -1420 | Cut, await line
2 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MANOS08 | DWJE MANOS 08 1000000099 5000006283 | 3000001132 | #VALUE! | CIRCULAR KNIT WOMEN'S TSHIRT | 4X3 RIB/96% ORGANIC COTTON 4% ELASTHANE/34S/ 230/ FABRIC DYED + PANEL WASHED | FABRIC DYE + PANEL WASH | 7000022450 | 1183 - SILKY WHITE | 1050 | 1050 | 04-MAR-2026 | 19-MAY-2026 | 05-MAY-2026 | 2026-03-25 | 2026-03-18 | 07-APR-2026 | 2026-03-18 | 13-APR-2026 | 2026-03-13 | 2026-03-13 | 1148 | 2026-04-27 | 2026-04-27 | 2026-04-30 | 2026-04-30 | 1145 | 2026-05-02 | 2026-04-16 | 2026-05-05 | 2026-04-25 |  | 1082 | 32 | OK. FI. Booking confirmed.
3 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MANOS08 | DWJE MANOS 08 1000000095 5000006278 | 3000000072 | #VALUE! | CIRCULAR KNIT WOMEN'S TANK TOP | 2X2 RIB/96% ORGANIC COTTON 4% ELASTHANE/50S/180// FABRIC DYED + PANEL WASHED | FABRIC DYE + PANEL WASH | 7000022449 | 1183 - SILKY WHITE | 760 | 760 | 04-MAR-2026 | 05-MAY-2026 | 28-APR-2026 | 01-APR-2026 | 2026-03-25 | 01-APR-2026 | 2026-03-13 | 06-APR-2026 | 2026-03-13 | 2026-04-10 | 850 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 848 | 2026-04-11 | 2026-04-16 | 2026-05-05 | 2026-04-25 |  | 809 | 49 | OK. FI. Booking confirmed.
4 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MANOS08 | DWJE MANOS 08 1000000099 5000007827 | 3000000459 | #VALUE! | CIRCULAR KNIT WOMEN'S TSHIRT | 4X3 RIB/96% ORGANIC COTTON 4% ELASTHANE/34S/ 230/FABRIC DYED + PANEL WASHED | FABRIC DYE + PANEL WASH | 7000022458 | 0001-BLACK | 1130 | 1130 | 04-MAR-2026 | 05-MAY-2026 | 28-APR-2026 | 01-APR-2026 | 2026-03-25 | 01-APR-2026 | 2026-03-13 | 06-APR-2026 | 2026-03-13 | 2026-03-13 | 1237 | 2026-03-20 | 2026-03-19 | 01-MAY-2026 | 2026-03-21 | 1236 | 2026-03-25 | 2026-04-20 | 2026-05-05 | 2026-04-25 |  |  | -1130 | Ready for FI; Booking received
5 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MANOS08 | DWJE MANOS 08 1000000099 5000007827 | 3000000459 | #VALUE! | CIRCULAR KNIT WOMEN'S TSHIRT | 4X3 RIB/96% ORGANIC COTTON 4% ELASTHANE/34S/ 230/FABRIC DYED + PANEL WASHED | FABRIC DYE + PANEL WASH | 7000022456, 7000022457 | 1183-SILKY WHITE | 1770 | 2270 | 04-MAR-2026 | 19-MAY-2026 | 05-MAY-2026 | 07-APR-2026 | 2026-03-25 | 07-APR-2026 | 2026-03-25 | 2026-03-27 | 2026-03-30 | 2026-03-30 | 1885 | 2026-04-15 | 2026-04-08 | 2026-04-20 |  |  | 2026-04-23 |  | 2026-05-27 |  |  |  | -1770 | U/ sewing.
[11 empty] | 4133 - BLUE DEPTHS | 500 | [7 empty] | 2026-03-28 |  |  |  | 570 | [11 empty] | -500
Grand Total | [12 empty] | 6630 | [10 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0 | -6630