## Sheet 1
Marc O'Polo Women Casual W26(1) 608 - 609 Order status Report - Bulk Production | [29 empty] | Report Generated Date: 26/12/2025 16:12
S.No | Buyer | Factory | Customer Season | Style No | Image | Style Description | Fabric Quality | Treatment | Buyer Po No | Color | Quantity |  | Original order received Dt | Etd Ex factory as per P.O | Factory Confirmed Dt | Trims Inhouse |  | Fabric Inhouse |  | PPS Submission |  |  | Cut Qty | Sewing Start |  | Sewing End |  | Sewing Qty | Inspection |  | Ex Factory Shipment |  |  | Shipped Qty | Balance Qty | Remarks
[11 empty] | Col | Qty |  |  |  | Planned | Actual | Planned | Actual | Planned | Actual | PPS Approved |  | Planned | Actual | Planned | Actual |  | Planned | Actual | Planned | Actual | Extended
1 | MARC O'POLO INTERNATIONAL GMBH | BVK EXPORTS INDIA PRIVATE LIMITED | CE08 | CWJE FW26 08 1000002497 5000014861 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | 2X2 RIB/96% ORGANIC COTTON 4% ELASTHANE/36S/220/FABRIC DYED | FABRIC DYE + PANEL WASH | 7000018312 | 0001, | 745 | 2766 | 25-DEC-2025 | 10-MAY-2026 | 14-APR-2026 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 07-MAR-2026 |  | 25-DEC-2025 | 772 | 2026-03-30 | 2026-03-30 | 2026-04-10 | 2026-04-10 | 770 | 2026-04-21 |  | 10-MAY-2026 |  |  |  | -745 | BULK UNDER FINISHING
[10 empty] | 636 | 563 | [11 empty] | 594 |  |  |  |  | 589 | [6 empty] | -563
[10 empty] | 1180-WHITE COTTON | 745 | [11 empty] | 770 |  |  |  |  | 766 | [6 empty] | -745
[10 empty] | 4300 | 713 | [11 empty] | 748 |  |  |  |  | 745 | [6 empty] | -713
2 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | CE08 | CWJE FW26 08 1000000710 5000014859 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SLUB JERSEY/100% ORGANIC COTTON/20S/155/FABRIC DYED | FABRIC DYE + PANEL WASH | 7000018304, 7000018305 | 1180-WHITE COTTON | 1710 | 3502 | 25-DEC-2025 | 10-MAY-2026 | 14-APR-2026 | 2026-02-17 | 2026-02-17 | 2026-01-30 | 2026-01-30 | 07-MAR-2026 |  | 25-DEC-2025 | 1795 | 2026-03-09 | 2026-03-09 | 2026-03-18 | 2026-03-18 | 1790 | 2026-03-30 | 2026-03-30 | 10-MAY-2026 | 2026-04-10 |  | 1760 | 50 | SHIPPED
[10 empty] | 3824 | 1024 | [11 empty] | 1076 |  |  |  |  | 1070 | [5 empty] | 1057 | 33
[10 empty] | 3187 | 768 | [11 empty] | 810 |  |  |  |  | 810 | [5 empty] | 814 | 46
3 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | CE08 | CWJE FW26 08 1000002498 5000014867 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SINGLE JERSEY STRETCH/95% ECOVERA VISCOSE 5% ELASTHANE/40S/20D///32GG/190//RFD | FABRIC DYE + PANEL WASH | 7000018313, 7000018314 | 2532 | 1260 | 2255 | 25-DEC-2025 | 10-MAY-2026 | 14-APR-2026 | 2026-02-17 | 2026-02-17 | 2026-02-13 | 2026-02-13 | 07-MAR-2026 |  | 25-DEC-2025 | 1312 | 2026-04-06 | 2026-04-06 | 2026-04-17 | 2026-04-17 | 1303 | 2026-04-20 |  | 10-MAY-2026 |  |  |  | -1260 | BULK UNDER FINISHING
[10 empty] | 4792 | 995 | [11 empty] | 1048 |  |  |  |  | 880 | [6 empty] | -995
4 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | CE08 | CWJE FW26 07 1000001294 5000016422 | #VALUE! | CIRCULAR KNIT WOMENS SWEAT SHIRT | FRENCH TERRY/100% ORGANIC COTTON/34S/34S/12S//20GG/290//FABRIC DYED + PEACHED + PANEL WASH | FABRIC DYED + INSIDE BRUSHED+ PEACHED + PANEL WASH | 7000018310, 7000018311 | 4300 | 1250 | 2900 | 25-DEC-2025 | 10-MAY-2026 | 14-APR-2026 | 2026-02-17 | 2026-02-17 | 2026-02-13 | 2026-02-13 | 07-MAR-2026 |  | 25-DEC-2025 | 1312 | 2026-03-20 | 2026-03-20 | 2026-03-27 | 2026-03-27 | 1310 | 2026-04-06 | 2026-04-06 | 10-MAY-2026 | 2026-04-10 |  | 1317 | 67 | SHIPPED
[10 empty] | 5561 | 600 | [11 empty] | 636 |  |  |  |  | 630 | [5 empty] | 625 | 25
[10 empty] | 8196 | 1050 | [11 empty] | 1102 |  |  |  |  | 1100 | [5 empty] | 1090 | 40
5 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | CE08 | CWJE FW26 07 1000000711 5000016416 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SZ SLUB JERSEY/100% ORGANIC COTTON/20S/155/YARN DYED + PANEL WASH | YARN DYED + PANEL WASH | 7000018306, 7000018307 | 1543 | 1950 | 8260 | 25-DEC-2025 | 10-MAY-2026 | 14-APR-2026 | 2026-02-17 | 2026-02-17 | 2026-02-10 | 2026-02-10 | 07-MAR-2026 |  | 25-DEC-2025 | 2020 | 2026-03-07 | 2026-03-07 | 2026-03-24 | 2026-03-24 | 2016 | 2026-03-07 | 2026-03-07 | 10-MAY-2026 | 2026-04-10 |  | 2070 | 120 | SHIPPED
[10 empty] | 1837 | 2210 | [11 empty] | 2292 |  |  |  |  | 2280 | [5 empty] | 2336 | 126
[10 empty] | 5138 | 2350 | [11 empty] | 2460 |  |  |  |  | 2448 | [5 empty] | 2487 | 137
[10 empty] | 7027 | 1750 | [11 empty] | 1824 |  |  |  |  | 1817 | [5 empty] | 1839 | 89
6 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | CE08 | CWJE FW26 07 1000000711 5000016417 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SZ SLUB JERSEY/100% ORGANIC COTTON/20S/155/YARN DYED + PANEL WASH | YARN DYED + PANEL WASH | 7000018308, 7000018309 | 1543 | 210 | 2761 | 25-DEC-2025 | 10-MAY-2026 | 14-APR-2026 | 2026-02-17 | 2026-02-17 | 2026-02-10 | 2026-02-10 | 07-MAR-2026 |  | 25-DEC-2025 | 232 | 2026-03-10 | 2026-03-10 | 2026-03-18 | 2026-03-18 | 232 | 2026-04-06 | 2026-04-06 | 10-MAY-2026 | 2026-04-10 |  | 224 | 14 | SHIPPED
[10 empty] | 4928 | 885 | [11 empty] | 946 |  |  |  |  | 943 | [5 empty] | 941 | 56
[10 empty] | 5138 | 753 | [11 empty] | 804 |  |  |  |  | 803 | [5 empty] | 797 | 44
[10 empty] | 7027 | 913 | [11 empty] | 950 |  |  |  |  | 949 | [5 empty] | 949 | 36
7 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | CWJE FW26 08 1000001160 5000014807 | #VALUE! | CIRCULAR KNIT WOMENS TANK TOP | SINGLE JERSEY/96% ORGANIC COTTON 4% ELASTHANE/40S////28GG/160/20D/FABRIC DYED | FABRIC DYED | 7000020120, 7000020608, 7000021044 | 1671-STONE TAUPE | 376 | 972 | 17-FEB-2026 | 01-MAY-2026 | 22-APR-2026 | 2026-03-20 | 2026-03-20 | 2026-03-12 | 2026-03-09 | 28-MAR-2026 |  | 17-FEB-2026 | 396 | 2026-04-02 | 2026-04-02 | 2026-04-04 | 2026-04-04 | 396 | 2026-04-08 | 2026-04-08 | 01-MAY-2026 | 2026-04-13 |  | 406 | 30 | SHIPPED
[10 empty] | 6939-BLACK CHERRY | 596 | [7 empty] | 2026-03-12 |  |  |  | 630 |  |  |  |  | 626 | [5 empty] | 624 | 28
8 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | CWJE FW26 08 1000002021 5000012911 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SINGLE JERSEY/65% LYOCELL 35% ORGANIC COTTON/32S////28GG/160//RFD | GARMENT DYED | 7000020097, 7000020288, 7000020523, 7000020947 | 0915-NATURAL | 1412 | 3549 | 17-FEB-2026 | 10-MAY-2026 | 22-APR-2026 | 2026-03-20 | 2026-03-20 | 2026-03-28 | 2026-03-28 | 02-APR-2026 |  | 17-FEB-2026 |  | 2026-04-21 |  | 2026-04-28 |  |  | 2026-05-05 |  | 10-MAY-2026 |  |  |  | -1412 | BULK UNDER CUTTING
[10 empty] | 6939-BLACK CHERRY | 1890 | [23 empty] | -1890
[10 empty] | 8168-MISTY ROSE | 247 | [23 empty] | -247
9 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | CWJE FW26 08 1000002021 5000012914 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SINGLE JERSEY/65% LYOCELL 35% ORGANIC COTTON/32S////28GG/160//RFD | GARMENT DYED | 7000020098, 7000020289, 7000020531, 7000020705, 7000020956 | 0915-NATURAL | 137 | 1104 | 17-FEB-2026 | 10-MAY-2026 | 22-APR-2026 | 2026-03-20 | 2026-03-20 | 2026-04-02 | 2026-04-02 | 02-APR-2026 |  | 17-FEB-2026 | 150 | 2026-04-17 | 2026-04-17 | 2026-04-21 |  |  | 2026-05-29 |  | 10-MAY-2026 |  |  |  | -137 | BULK UNDER SEWING
[10 empty] | 1671-STONE TAUPE | 566 | [11 empty] | 600 | [11 empty] | -566
[10 empty] | 6939-BLACK CHERRY | 401 | [11 empty] | 436 | [11 empty] | -401
10 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | CWJE FW26 08 1000002021 5000012918 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SINGLE JERSEY/65% LYOCELL 35% ORGANIC COTTON/32S////28GG/160//RFD | GARMENT DYED | 7000020100, 7000020296, 7000020537, 7000020964 | 0915-NATURAL | 2798 | 7048 | 18-FEB-2026 | 12-MAY-2026 | 22-APR-2026 | 2026-03-20 | 2026-03-20 | 2026-04-22 | 2026-04-15 | 03-APR-2026 |  | 2026-03-16 |  | 2026-04-24 |  | 2026-05-14 |  |  | 2026-05-25 |  | 12-MAY-2026 |  |  |  | -2798 | BULK FABRIC UNDER PROCESS
[10 empty] | 1671-STONE TAUPE | 679 | [7 empty] | 2026-04-16 | [15 empty] | -679
[10 empty] | 6939-BLACK CHERRY | 3295 | [23 empty] | -3295
[10 empty] | 8168-MISTY ROSE | 276 | [7 empty] | 2026-04-17 | [15 empty] | -276
11 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | CWJE FW26 08 1000000711 5000012510 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SZ SLUB JERSEY/100% ORGANIC COTTON/20S/155/YARN DYED + PANEL WASH | YARN DYED + PANEL WASH | 7000020087, 7000020282, 7000020463, 7000020665, 7000020871 | 2446-MEDIUM BEIGE_MULTI | 1292 | 2817 | 17-FEB-2026 | 01-JUN-2026 | 12-MAY-2026 | 2026-03-20 | 2026-03-20 | 2026-03-26 | 2026-03-26 | 12-APR-2026 |  | 17-FEB-2026 |  | 2026-04-24 |  | 2026-04-28 |  |  | 2026-05-05 |  | 01-JUN-2026 |  |  |  | -1292 | BULK FABRIC UNDER CUTTING
[10 empty] | 4445-DARK BLUE_MULTI | 451 | [6 empty] | 2026-03-28 | 2026-03-28 | [15 empty] | -451
[10 empty] | 7030-DARK RED_MULTI | 568 | [6 empty] | 2026-03-30 | 2026-03-30 | [15 empty] | -568
[10 empty] | 7941-MEDIUM PINK_MULTI | 506 | [6 empty] | 2026-03-26 | 2026-03-26 | [15 empty] | -506
12 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | CWJE FW26 08 1000001294 5000012511 | #VALUE! | CIRCULAR KNIT WOMENS SWEAT SHIRT | FRENCH TERRY/100% ORGANIC COTTON/34S/34S/12S//20GG/290//FABRIC DYED + PEACHED + PANEL WASH | FABRIC DYED + PEACHED + PANEL SOFTENER WASH | 7000020088, 7000020472, 7000020675, 7000020879 | 0915-NATURAL | 552 | 2489 | 17-FEB-2026 | 01-JUN-2026 | 12-MAY-2026 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 12-APR-2026 |  | 17-FEB-2026 | 580 | 2026-04-21 |  | 2026-04-27 |  |  | 2026-05-04 |  | 01-JUN-2026 |  |  |  | -552 | BULK READY FOR SEWING
[10 empty] | 4143-MARTIME BLUE | 679 | [11 empty] | 710 | [11 empty] | -679
[10 empty] | 6939-BLACK CHERRY | 725 | [11 empty] | 760 | [11 empty] | -725
[10 empty] | 7811-BERRY ROSE | 533 | [11 empty] | 562 | [11 empty] | -533
13 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | CWJE FW26 08 1000001294 5000012512 | #VALUE! | CIRCULAR KNIT WOMENS HOODED SWEAT SHIRT | FRENCH TERRY/100% ORGANIC COTTON/34S/34S/12S//20GG/290//FABRIC DYED + PEACHED + PANEL WASH | FABRIC DYED + PEACHED + PANEL SOFTENER WASH | 7000020089, 7000020486, 7000020682, 7000020886, 7000020913 | 0915-NATURAL | 588 | 3332 | 17-FEB-2026 | 01-JUN-2026 | 12-MAY-2026 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 12-APR-2026 |  | 17-FEB-2026 | 620 | 2026-03-30 | 2026-03-30 | 2026-04-10 | 2026-04-10 | 620 | 2026-04-21 |  | 01-JUN-2026 |  |  |  | -588 | BULK UNDER FINISHING
[10 empty] | 4143-MARTIME BLUE | 691 | [11 empty] | 728 |  |  |  |  | 725 | [6 empty] | -691
[10 empty] | 6939-BLACK CHERRY | 1327 | [11 empty] | 1400 |  |  |  |  | 1390 | [6 empty] | -1327
[10 empty] | 7811-BERRY ROSE | 726 | [11 empty] | 772 |  |  |  |  | 770 | [6 empty] | -726
14 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | CWJE FW26 08 1000001294 5000012513 | #VALUE! | CIRCULAR KNIT WOMENS SWEAT PANT | FRENCH TERRY/100% ORGANIC COTTON/34S/34S/12S//20GG/290//FABRIC DYED + PEACHED + PANEL WASH | FABRIC DYED + PEACHED + PANEL SOFTENER WASH | 7000020090, 7000020689, 7000020918 | 4143-MARTIME BLUE | 334 | 559 | 17-FEB-2026 | 01-JUN-2026 | 12-MAY-2026 | 2026-03-20 | 2026-03-20 | 2026-03-19 | 2026-03-19 | 13-APR-2026 |  | 17-FEB-2026 | 368 | 2026-04-17 | 2026-04-17 | 2026-04-21 |  |  | 2026-04-27 |  | 01-JUN-2026 |  |  |  | -334 | BULK UNDER SEWING
[10 empty] | 6939-BLACK CHERRY | 225 | [11 empty] | 248 | [11 empty] | -225
15 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | CWJE FW26 08 1000002029 5000012500 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | 3X1 RIB/64% LYOCELL 31% ORGANIC COTTON 5% ELASTHANE/50S/20D///28GG/180//RFD | GARMENT DYED | 7000020069, 7000020194, 7000020415, 7000020635, 7000020772 | 0915-NATURAL | 2349 | 6034 | 17-FEB-2026 | 01-JUN-2026 | 12-MAY-2026 | 2026-03-20 | 2026-03-20 | 2026-04-03 | 2026-04-03 | 13-APR-2026 |  | 17-FEB-2026 | 2490 | 2026-04-21 |  | 2026-04-30 |  |  | 2026-05-09 |  | 01-JUN-2026 |  |  |  | -2349 | BULK UNDER SEWING
[10 empty] | 1671-STONE TAUPE | 1935 | [11 empty] | 2032 | [11 empty] | -1935
[10 empty] | 6939-BLACK CHERRY | 1750 | [11 empty] | 1818 | [11 empty] | -1750
16 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | CWJE FW26 08 1000002029 5000012499 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | 3X1 RIB/64% LYOCELL 31% ORGANIC COTTON 5% ELASTHANE/50S/20D///28GG/180//RFD | GARMENT DYED | 7000020068, 7000020189, 7000020412, 7000020627, 7000020760 | 0915-NATURAL | 607 | 4189 | 17-FEB-2026 | 01-JUN-2026 | 12-MAY-2026 | 2026-03-20 | 2026-03-20 | 2026-03-30 | 2026-03-30 | 13-APR-2026 |  | 17-FEB-2026 | 648 | 2026-04-18 | 2026-04-18 | 2026-04-29 |  |  | 2026-05-10 |  | 01-JUN-2026 |  |  |  | -607 | BULK UNDER SEWING
[10 empty] | 1671-STONE TAUPE | 1399 | [11 empty] | 1540 | [11 empty] | -1399
[10 empty] | 6939-BLACK CHERRY | 1143 | [11 empty] | 1236 | [11 empty] | -1143
[10 empty] | 8168-MISTY ROSE | 1040 | [11 empty] | 1120 | [11 empty] | -1040
17 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | CWJE FW26 08 1000002029 5000012501 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | 3X1 RIB/64% LYOCELL 31% ORGANIC COTTON 5% ELASTHANE/50S/20D///28GG/180//RFD | GARMENT DYED | 7000020071, 7000020647, 7000020778 | 0915-NATURAL | 392 | 755 | 17-FEB-2026 | 01-JUN-2026 | 12-MAY-2026 | 2026-03-20 | 2026-03-20 | 2026-03-26 | 2026-03-26 | 13-APR-2026 |  |  | 430 | 2026-04-20 | 2026-04-20 | 2026-04-23 |  |  | 2026-05-05 |  | 01-JUN-2026 |  |  |  | -392 | BULK UNDER SEWING
[10 empty] | 6939-BLACK CHERRY | 363 | [11 empty] | 396 | [11 empty] | -363
18 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | CWJE FW26 08 1000000710 5000012508 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SLUB JERSEY/100% ORGANIC COTTON/20S/155/FABRIC DYED | FABRIC DYED | 7000020078, 7000020234, 7000020446, 7000020663, 7000020818 | 0915-NATURAL | 724 | 3249 | 17-FEB-2026 | 01-JUN-2026 | 12-MAY-2026 | 2026-03-20 | 2026-03-20 | 2026-03-07 | 2026-03-07 | 13-APR-2026 |  | 17-FEB-2026 |  | 2026-04-27 |  | 2026-05-04 |  |  | 2026-05-08 |  | 01-JUN-2026 |  |  |  | -724 | BULK FABRIC READY TO CUT
[10 empty] | 4143-MARTIME BLUE | 715 | [23 empty] | -715
[10 empty] | 6939-BLACK CHERRY | 1264 | [23 empty] | -1264
[10 empty] | 8168-MISTY ROSE | 546 | [23 empty] | -546
19 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | CWJE FW26 08 1000000710 5000012507 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SLUB JERSEY/100% ORGANIC COTTON/20S/155/FABRIC DYED | FABRIC DYED | 7000020072, 7000020197, 7000020422, 7000020652, 7000020789 | 0915-NATURAL | 686 | 13757 | 17-FEB-2026 | 01-JUN-2026 | 12-MAY-2026 | 2026-03-20 | 2026-03-20 | 2026-03-12 | 2026-03-05 | 13-APR-2026 |  | 17-FEB-2026 | 708 | 2026-03-23 | 2026-03-23 | 2026-04-27 |  |  | 2026-05-06 |  | 01-JUN-2026 |  |  |  | -686 | BULK UNDER SEWING
[10 empty] | 1180-WHITE COTTON | 770 | [7 empty] | 2026-03-05 |  |  |  | 798 | [11 empty] | -770
[10 empty] | 1671-STONE TAUPE | 2651 | [7 empty] | 2026-03-05 |  |  |  | 2710 | [11 empty] | -2651
[10 empty] | 4783-STORMY SEA | 1078 | [7 empty] | 2026-03-12 |  |  |  | 1108 | [11 empty] | -1078
[10 empty] | 6939-BLACK CHERRY | 4976 | [7 empty] | 2026-03-07 |  |  |  | 3000 | [11 empty] | -4976
[10 empty] | 7811-BERRY ROSE | 2906 | [7 empty] | 2026-03-06 |  |  |  | 3180 | [11 empty] | -2906
[10 empty] | 8168-MISTY ROSE | 690 | [7 empty] | 2026-03-14 |  |  |  | 748 | [11 empty] | -690
20 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA08 | CWJE FW26 08 1000000711 5000012509 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SZ SLUB JERSEY/100% ORGANIC COTTON/20S/155/YARN DYED + PANEL WASH | YARN DYED + PANEL WASH | 7000020080, 7000020248, 7000020452, 7000020829 | 0828 | 4144 | 24864 | 18-FEB-2026 | 01-JUN-2026 | 12-MAY-2026 | 2026-03-20 | 2026-03-20 | 2026-03-23 | 2026-03-14 | 13-APR-2026 |  | 18-FEB-2026 | 4372 | 2026-03-25 | 2026-03-25 | 2026-04-23 |  |  | 2026-04-30 |  | 01-JUN-2026 |  |  |  | -4144 | BULK UNDER SEWING
[10 empty] | 2446-MEDIUM BEIGE | 8509 | [7 empty] | 2026-03-12 |  |  |  | 6000 | [11 empty] | -8509
[10 empty] | 4931-MEDIUM BLUE_MULTI | 642 | [7 empty] | 2026-03-16 |  |  |  | 672 | [11 empty] | -642
[10 empty] | 7030-DARK RED_MULTI | 4200 | [7 empty] | 2026-03-16 |  |  |  | 2800 | [11 empty] | -4200
[10 empty] | 7941-MEDIUM PINK_MULTI | 5158 | [7 empty] | 2026-03-20 | [15 empty] | -5158
[10 empty] | 7945 | 2211 | [7 empty] | 2026-03-27 |  |  |  | 2380 | [11 empty] | -2211
21 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA09 | CWJE FW26 09 1000000711 5000014798 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SZ SLUB JERSEY/100% ORGANIC COTTON/20S/155/YARN DYED + PANEL WASH | YARN DYED + PANEL WASH | 7000020112, 7000020340, 7000020573, 7000020736, 7000021014 | 1544-DARK BROWN_MULTI | 10844 | 23624 | 18-FEB-2026 | 11-JUN-2026 | 26-MAY-2026 | 2026-03-20 | 2026-03-20 | 2026-04-22 |  | 19-APR-2026 |  | 18-FEB-2026 |  | 2026-05-05 |  | 2026-05-20 |  |  | 2026-05-24 |  | 11-JUN-2026 |  |  |  | -10844 | BULK FABRIC READY TO CUT
[10 empty] | 1839-MID BROWN_MULTI | 687 | [7 empty] | 2026-04-20 | [15 empty] | -687
[10 empty] | 3060-DARK GREEN_MULTI | 567 | [23 empty] | -567
[10 empty] | 3665-BRIGHT GREEN_MULTI | 3972 | [23 empty] | -3972
[10 empty] | 4444-DARK BLUE_MULTI | 3982 | [23 empty] | -3982
[10 empty] | 5701-LIGHT BLUE-MULTI | 3025 | [23 empty] | -3025
[10 empty] | 3494-MID GREEN_MULTI | 547 | [23 empty] | -547
22 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA09 | CWJE FW26 09 1000000711 5000012509 | #VALUE! | CIRCULAR KNIT WOMENS T SHIRT | SZ SLUB JERSEY/100% ORGANIC COTTON/20S/155/YARN DYED + PANEL WASH | YARN DYED + PANEL WASH | 7000020084, 7000020272, 7000020457, 7000020848 | 1544-DARK BROWN_MULTI | 1040 | 3299 | 18-FEB-2026 | 11-JUN-2026 | 26-MAY-2026 | 2026-03-20 | 2026-03-20 | 2026-04-20 | 2026-04-20 | 19-APR-2026 |  | 18-FEB-2026 |  | 2026-05-02 |  | 2026-05-07 |  |  | 2026-05-20 |  | 11-JUN-2026 |  |  |  | -1040 | BULK FABRIC READY TO CUT
[10 empty] | 1839-MID BROWN_MULTI | 573 | [23 empty] | -573
[10 empty] | 3060-DARK GREEN_MULTI | 123 | [23 empty] | -123
[10 empty] | 3494-MID GREEN_MULTI | 459 | [23 empty] | -459
[10 empty] | 3665-BRIGHT GREEN_MULTI | 70 | [23 empty] | -70
[10 empty] | 4444-DARK BLUE_MULTI | 681 | [23 empty] | -681
[10 empty] | 5701-LIGHT BLUE-MULTI | 353 | [23 empty] | -353
23 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA09 | CWJE FW26 09 1000000710 5000014799 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SLUB JERSEY/100% ORGANIC COTTON/20S/155/FABRIC DYED | FABRIC DYE + PANEL WASH | 7000020115, 7000020364, 7000020590, 7000020742, 7000021031 | 0344-BURNT COFFEE | 10833 | 27072 | 18-FEB-2026 | 11-JUN-2026 | 26-MAY-2026 | 2026-03-20 | 2026-03-20 | 2026-04-22 | 2026-04-16 | 19-APR-2026 |  | 18-FEB-2026 |  | 2026-05-04 |  | 2026-05-26 |  |  | 2026-05-30 |  | 11-JUN-2026 |  |  |  | -10833 | BULK FABRIC UNDER PROCESS
[10 empty] | 0475-COAL GREY MELANGE | 4734 | [7 empty] | 2026-04-20 | [15 empty] | -4734
[10 empty] | 0901-GLACIAL BLUE | 4560 | [23 empty] | -4560
[10 empty] | 2539-SMOKY SANDS | 1334 | [7 empty] | 2026-03-28 | [15 empty] | -1334
[10 empty] | 2910-QUIET PINE | 2987 | [23 empty] | -2987
[10 empty] | 3725-SMOOTH SAGE | 2624 | [7 empty] | 2026-04-15 | [15 empty] | -2624
24 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MA09 | CWJE FW26 09 1000000710 5000012507 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SLUB JERSEY/100% ORGANIC COTTON/20S/155/FABRIC DYED | FABRIC DYED | 7000020077, 7000020212, 7000020436, 7000020657, 7000020808 | 0344-BURNT COFFEE | 2574 | 6547 | 18-FEB-2026 | 11-JUN-2026 | 26-MAY-2026 | 2026-03-20 | 2026-03-20 | 2026-04-01 | 2026-03-23 | 19-APR-2026 |  | 18-FEB-2026 |  | 2026-04-27 |  | 2026-05-06 |  |  | 2026-05-18 |  | 11-JUN-2026 |  |  |  | -2574 | BULK FABRIC UNDER CUTTING
[10 empty] | 0901-GLACIAL BLUE | 1686 | [7 empty] | 2026-03-18 | [15 empty] | -1686
[10 empty] | 2539-SMOKY SANDS | 496 | [7 empty] | 2026-03-28 | [15 empty] | -496
[10 empty] | 3725-SMOOTH SAGE | 606 | [7 empty] | 2026-03-20 | [15 empty] | -606
[10 empty] | 2910-QUIET PINE | 1185 | [7 empty] | 2026-04-03 | [15 empty] | -1185
25 | MARC O'POLO INTERNATIONAL GMBH | BVK EXPORTS INDIA PRIVATE LIMITED | MA08 | CWJE FW26 08 1000002230 5000012521 | #VALUE! | CIRCULAR KNIT WOMENS DRESS | SINGLE JERSEY/93% ORGANIC COTTON 7% ELASTHANE/34S/30D///28GG/185//FABRIC DYED | FABRIC DYED | 7000020093, 7000020506, 7000020693, 7000020935 | 4143-MARTIME BLUE | 367 | 696 | 18-FEB-2026 | 10-MAY-2026 | 22-APR-2026 | 2026-03-25 | 2026-03-25 | 2026-03-14 | 2026-03-14 | 01-APR-2026 |  | 2026-03-23 | 396 | 2026-04-08 | 2026-04-08 | 2026-04-15 | 2026-04-15 | 392 | 2026-04-21 |  | 10-MAY-2026 |  |  |  | -367 | BULK UNDER FINISHING
[10 empty] | 6939-BLACK CHERRY | 329 | [11 empty] | 354 |  |  |  |  | 354 | [6 empty] | -329
26 | MARC O'POLO INTERNATIONAL GMBH | BVK EXPORTS INDIA PRIVATE LIMITED | MA08 | CWJE FW26 08 1000002230 5000014724 | #VALUE! | CIRCULAR KNIT WOMENS POLO SHIRT LONG SLEEVE | SINGLE JERSEY/93% ORGANIC COTTON 7% ELASTHANE/34S/30D///28GG/185//FABRIC DYED | FABRIC DYED | 7000020108, 7000020335, 7000020570, 7000020732, 7000021008 | 1180-WHITE COTTON | 475 | 5217 | 18-FEB-2026 | 12-MAY-2026 | 22-APR-2026 | 2026-03-25 | 2026-03-25 | 2026-03-27 | 2026-03-27 | 03-APR-2026 |  | 18-FEB-2026 | 500 | 2026-04-13 | 2026-04-13 | 2026-04-30 |  |  | 2026-05-04 |  | 12-MAY-2026 |  |  |  | -475 | BULK UNDER SEWING
[10 empty] | 4143-MARTIME BLUE | 673 | [7 empty] | 2026-03-14 |  |  |  | 710 | [11 empty] | -673
[10 empty] | 6939-BLACK CHERRY | 4069 | [7 empty] | 2026-03-14 |  |  |  | 4282 | [11 empty] | -4069
27 | MARC O'POLO INTERNATIONAL GMBH | BVK EXPORTS INDIA PRIVATE LIMITED | MA09 | CWJE FW26 09 1000001178 5000012881 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | 1X1 RIB/93% MODAL 7% ELASTHANE/50S/20D///18GG/185//FABRIC DYED | FABRIC DYED | 7000020094, 7000020514, 7000020699, 7000020942 | 0344-BURNT COFFEE | 2187 | 5186 | 18-FEB-2026 | 01-JUN-2026 | 26-MAY-2026 | 2026-03-25 | 2026-03-25 | 2026-04-15 | 2026-04-06 | 13-APR-2026 |  | 18-FEB-2026 |  | 2026-05-24 |  | 2026-05-04 |  |  | 2026-05-10 |  | 01-JUN-2026 |  |  |  | -2187 | BULK FABRIC UNDER CUTTING
[10 empty] | 1740-EARTHY TAUPE | 1173 | [7 empty] | 2026-04-09 | [15 empty] | -1173
[10 empty] | 2539-SMOKY SANDS | 1438 | [7 empty] | 2026-04-15 | [15 empty] | -1438
[10 empty] | 2910-QUIET PINE | 388 | [7 empty] | 2026-04-09 | [15 empty] | -388
28 | MARC O'POLO INTERNATIONAL GMBH | BVK EXPORTS INDIA PRIVATE LIMITED | MA09 | CWJE FW26 09 1000001178 5000012921 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | 1X1 RIB/93% MODAL 7% ELASTHANE/50S/20D///18GG/185//FABRIC DYED | FABRIC DYED | 7000020101, 7000020309, 7000020546, 7000020714, 7000020982 | 0001 BLACK | 1844 | 21832 | 18-FEB-2026 | 11-JUN-2026 | 26-MAY-2026 | 2026-03-25 | 2026-03-25 | 2026-04-15 | 2026-04-13 | 18-APR-2026 |  | 18-FEB-2026 | 1930 | 2026-04-20 | 2026-04-20 | 2026-05-25 |  |  | 2026-05-30 |  | 11-JUN-2026 |  |  |  | -1844 | BULK UNDER SEWING
[10 empty] | 0344-BURNT COFFEE | 10935 | [7 empty] | 2026-04-06 |  |  |  | 2500 | [11 empty] | -10935
[10 empty] | 0475-COAL GREY MELANGE | 2579 | [7 empty] | 2026-04-15 |  |  |  | 2700 | [11 empty] | -2579
[10 empty] | 1740-EARTHY TAUPE | 4378 | [7 empty] | 2026-04-15 |  |  |  | 2200 | [11 empty] | -4378
[10 empty] | 2539-SMOKY SANDS | 1592 | [7 empty] | 2026-04-09 | [15 empty] | -1592
[10 empty] | 2910-QUIET PINE | 504 | [7 empty] | 2026-04-09 |  |  |  | 530 | [11 empty] | -504
29 | MARC O'POLO INTERNATIONAL GMBH | BVK EXPORTS INDIA PRIVATE LIMITED | MA09 | CWJE FW26 09 1000002041 5000012981 | #VALUE! | CIRCULAR KNIT WOMENS POLO SHIRT LONG SLEEVE | SINGLE JERSEY/97% ORGANIC COTTON 3% ELASTHANE/24S/20D///16GG/180//FABRIC DYED + PEACHED + PANEL WASH | FABRIC DYED + PEACHED + PANEL SOFTENER WASH | 7000020107, 7000020326, 7000020564, 7000020727, 7000021001 | 0344-BURNT COFFEE | 2588 | 4736 | 18-FEB-2026 | 11-JUN-2026 | 26-MAY-2026 | 2026-03-25 | 2026-03-25 | 2026-04-22 |  | 18-APR-2026 |  | 18-FEB-2026 |  | 2026-05-02 |  | 2026-05-22 |  |  | 2026-05-28 |  | 11-JUN-2026 |  |  |  | -2588 | BULK FABRIC UNDER PROCESS
[10 empty] | 0925-FROSTY BLUE | 1659 | [23 empty] | -1659
[10 empty] | 3725-SMOOTH SAGE | 489 | [23 empty] | -489
30 | MARC O'POLO INTERNATIONAL GMBH | BVK EXPORTS INDIA PRIVATE LIMITED | MA09 | CWJE FW26 09 1000002041 5000012517 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SINGLE JERSEY/97% ORGANIC COTTON 3% ELASTHANE/24S/20D///16GG/180//FABRIC DYED + PEACHED + PANEL WASH | FABRIC DYED + PEACHED + PANEL SOFTENER WASH | 7000020092, 7000020284, 7000020501, 7000020932 | 0344-BURNT COFFEE | 1903 | 3698 | 18-FEB-2026 | 11-JUN-2026 | 26-MAY-2026 | 2026-03-25 | 2026-03-25 | 2026-04-21 |  | 18-APR-2026 |  | 18-FEB-2026 |  | 2026-04-28 |  | 2026-05-18 |  |  | 2026-05-22 |  | 11-JUN-2026 |  |  |  | -1903 | BULK FABRIC UNDER PROCESS
[10 empty] | 0925-FROSTY BLUE | 325 | [23 empty] | -325
[10 empty] | 3725-SMOOTH SAGE | 1470 | [23 empty] | -1470
31 | MARC O'POLO INTERNATIONAL GMBH | BVK EXPORTS INDIA PRIVATE LIMITED | MA09 | CWJE FW26 09 1000002230 5000012980 | #VALUE! | CIRCULAR KNIT WOMENS DRESS | SINGLE JERSEY/93% ORGANIC COTTON 7% ELASTHANE/34S/30D///28GG/185//FABRIC DYED | FABRIC DYED | 7000020104, 7000020995 | 0001 BLACK | 361 | 729 | 18-FEB-2026 | 11-JUN-2026 | 26-MAY-2026 | 2026-03-25 | 2026-03-25 | 2026-04-28 | 2026-03-13 | 18-APR-2026 |  | 2026-03-18 | 382 | 2026-04-10 | 2026-04-10 | 2026-04-13 | 2026-04-13 | 380 | 2026-04-21 |  | 11-JUN-2026 |  |  |  | -361 | BULK UNDER FINISHING
[10 empty] | 0344-BURNT COFFEE | 368 | [7 empty] | 2026-04-28 |  |  |  | 390 |  |  |  |  | 386 | [6 empty] | -368
32 | MARC O'POLO INTERNATIONAL GMBH | BVK EXPORTS INDIA PRIVATE LIMITED | MA09 | CWJE FW26 09 1000002040 5000012515 | #VALUE! | CIRCULAR KNIT WOMENS HOODED SWEAT SHIRT | FRENCH TERRY/100% ORGANIC COTTON/40S/2/10S///12GG/340//FABRIC DYED + BRUSHED | FABRIC DYE + INSIDE BRUSHED + PANEL WASH | 7000020091, 7000020926 | 0901-GLACIAL BLUE | 523 | 837 | 18-FEB-2026 | 11-JUN-2026 | 26-MAY-2026 | 2026-03-25 | 2026-03-25 | 2026-04-20 |  | 18-APR-2026 |  |  |  | 2026-05-10 |  | 2026-06-03 |  |  | 2026-06-10 |  | 11-JUN-2026 |  |  |  | -523 | BULK FABRIC UNDER PROCESS
[10 empty] | 1381-DARK WALNUT | 314 | [23 empty] | -314
Grand Total | [11 empty] | 200635 | [10 empty] | 89523 |  |  |  |  | 29290 | [5 empty] | 19336 | -181299