## Sheet 1
Marc O'Polo Women Casual BNOS W26(1) - MANOS07 - 08 Order status Report - Bulk Production
S.No | Buyer | Factory | Customer Season | Style No | Image | Style Description | Fabric Quality | Treatment | Buyer Po No | Color | Quantity |  | Original order received Dt | Etd Ex factory as per P.O | Factory Confirmed Dt | Trims Inhouse |  | Fabric Inhouse |  | PPS Submission |  |  | Cut Qty | Sewing Start |  | Sewing End |  | Sewing Qty | Inspection |  | Ex Factory Shipment |  |  | Shipped Qty | Balance Qty | Remarks
[11 empty] | Col | Qty |  |  |  | Planned | Actual | Planned | Actual | Planned | Actual | PPS Approved |  | Planned | Actual | Planned | Actual |  | Planned | Actual | Planned | Actual | Extended
1 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MANOS07 | CWJE NOS 90 1000000711 5000009474 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SZ SLUB JERSEY/100% ORGANIC COTTON/20S/155/YARN DYED + PANEL WASH | YARN DYED + PANEL WASH | 7000022247, 7000022248 | 4441 DARK BLUE - MULTI 02 | 670 | 1230 | 26-FEB-2026 | 29-APR-2026 | 21-APR-2026 | 2026-03-20 | 2026-03-20 | 2026-02-26 | 2026-02-26 | 31-MAR-2026 |  | 26-FEB-2026 | 710 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | 708 | 2026-04-07 | 2026-04-07 | 29-APR-2026 | 2026-04-10 |  | 704 | 34 | SHIPPED
[10 empty] | 2673-LIGHT BEIGE MULTI01 | 560 | [11 empty] | 606 |  |  |  |  | 600 | [5 empty] | 598 | 38
2 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MANOS07 | CWJE NOS 90 1000001172 5000009473 | #VALUE! | CIRCULAR KNIT WOMENS TANK TOP | 1X1 RIB/100% ORGANIC COTTON/48S////24GG/170//FABRIC DYED + PANEL WASHED | FABRIC DYE + PANEL WASH | 7000022237, 7000022238 | 0163 WHITE | 870 | 1530 | 26-FEB-2026 | 29-APR-2026 | 21-APR-2026 | 2026-03-20 | 2026-03-20 | 2026-03-14 | 2026-03-14 | 31-MAR-2026 |  | 26-FEB-2026 | 940 | 2026-03-31 | 2026-03-31 | 2026-04-02 | 2026-04-02 | 936 | 2026-04-14 | 2026-04-14 | 29-APR-2026 | 2026-04-20 |  | 930 | 60 | SHIPPED
[10 empty] | 4127-MANIAC MIDNIGHT | 660 | [6 empty] | 2026-02-26 | 2026-02-26 |  |  |  | 716 |  |  |  |  | 715 | [5 empty] | 711 | 51
3 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MANOS07 | CWJE NOS 90 1000001160 5000009467 | #VALUE! | CIRCULAR KNIT WOMENS TANK TOP | SINGLE JERSEY/96% ORGANIC COTTON 4% ELASTHANE/40S////28GG/160/20D/FABRIC DYED | FABRIC DYED | 7000022206 | 0163 WHITE | 420 | 420 | 26-FEB-2026 | 29-APR-2026 | 21-APR-2026 | 2026-03-20 | 2026-03-20 | 2026-02-26 | 2026-02-26 | 31-MAR-2026 |  | 26-FEB-2026 | 454 | 2026-04-03 | 2026-04-03 | 2026-04-04 | 2026-04-04 | 450 | 2026-04-16 | 2026-04-16 | 29-APR-2026 | 2026-04-20 |  | 449 | 29 | SHIPPED
4 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MANOS08 | CWJE NOS 90 1000000710 5000009477 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SLUB JERSEY/100% ORGANIC COTTON/20S/155/FABRIC DYED | FABRIC DYE + PANEL WASH | 7000022249, 7000022251, 7000022252 | 0163 WHITE | 2100 | 4490 | 26-FEB-2026 | 10-MAY-2026 | 28-APR-2026 | 2026-03-20 | 2026-03-20 | 2026-02-26 | 2026-02-26 | 06-APR-2026 |  | 26-FEB-2026 | 2210 | 2026-03-24 | 2026-03-24 | 2026-03-28 | 2026-03-28 | 2208 | 2026-04-13 | 2026-04-13 | 10-MAY-2026 |  |  | 2206 | 106 | READY TO SHIP
[10 empty] | 4127-MANIAC MIDNIGHT | 1760 | [11 empty] | 1874 |  |  |  |  | 1870 | [5 empty] | 1863 | 103
[10 empty] | 0001 BLACK | 630 | [11 empty] | 692 |  |  |  |  | 690 | [5 empty] | 679 | 49
5 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MANOS08 | CWJE NOS 90 1000000710 5000009478 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SLUB JERSEY/100% ORGANIC COTTON/20S/155/FABRIC DYED | FABRIC DYE + PANEL WASH | 7000022254, 7000022255, 7000022256 | 0163 WHITE | 5200 | 6840 | 26-FEB-2026 | 10-MAY-2026 | 28-APR-2026 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 2026-03-20 | 06-APR-2026 |  | 26-FEB-2026 | 5480 | 2026-04-01 | 2026-04-01 | 2026-04-09 | 2026-04-09 | 5468 | 2026-04-24 |  | 10-MAY-2026 |  |  |  | -5200 | BULK UNDER FINISHING
[10 empty] | 4127-MANIAC MIDNIGHT | 1050 | [6 empty] | 2026-02-26 | 2026-02-26 |  |  |  | 1110 |  |  |  |  | 1102 | [6 empty] | -1050
[10 empty] | 0001 BLACK | 590 | [6 empty] | 2026-02-26 | 2026-02-26 |  |  |  | 630 |  |  |  |  | 630 | [6 empty] | -590
6 | MARC O'POLO INTERNATIONAL GMBH | WARSAW INTERNATIONAL | MANOS09 | CWJE NOS 90 1000000710 5000009477 | #VALUE! | CIRCULAR KNIT WOMENS TSHIRT | SLUB JERSEY/100% ORGANIC COTTON/20S/155/FABRIC DYED | FABRIC DYE + PANEL WASH | 7000023237, 7000023238 | 0163 WHITE | 1270 | 2230 | 26-MAR-2026 | 11-JUN-2026 | 19-MAY-2026 | 2026-04-16 | 2026-04-16 | 2026-04-10 | 2026-04-10 | 05-MAY-2026 |  | 26-MAR-2026 |  | 2026-05-06 |  | 2026-05-09 |  |  | 2026-05-12 |  | 11-JUN-2026 |  |  |  | -1270 | BULK FABRIC READY TO CUT
[10 empty] | 4127-MANIAC MIDNIGHT | 960 | [23 empty] | -960
Grand Total | [11 empty] | 16740 | [10 empty] | 15422 |  |  |  |  | 15377 | [5 empty] | 8140 | -8600