## Sheet1
Orders Plan
Date : | 2026-04-21 |  | Order receipt | 2026-02-06 |  | Order L/D | 90
Job No | 63261 |  | Ex-Fty date | 2026-05-07 |  | Pre-Prod L/D | 49.5
Quantity : | 16200 |  | Delivery date | 2026-05-17 |  | Prodn L/D | 40.5
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-02-13 10:12 | 2026-02-25 19:12 | 2026-02-13 10:12 | 2026-03-02 18:00 | 2026-02-18 09:00 | 2026-03-07 16:48 | 2026-03-09 04:26 | 2026-03-12 15:36 | 2026-03-17 14:24 | 2026-03-25 00:36 | 2026-03-20 01:48 | 2026-03-29 23:24 | 2026-03-27 12:00
| Action | CLAER | CLAER | CLAER | CLAER | CLAER | CLAER | CLAER | CLAER | CLAER | CLAER | CLAER | CLAER | CLAER
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-02-07 23:31 | 2026-02-10 22:48 | 2026-02-10 22:48 | 2026-02-12 10:26 | 2026-02-18 09:00 | 2026-02-20 20:24 | 2026-03-01 18:14 | 2026-03-02 18:00 | 2026-03-16 14:38 | 2026-03-16 14:38 | 2026-03-19 02:02 | 2026-03-20 01:48
| Action | CLAER | CLAER | CLAER | CLAER | CLAER | CLAER | CLAER | CLAER | CLAER | CLAER | CLAER | CLAER
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-27 12:00 | 2026-03-30 12:00 | 2026-04-21 | 2026-04-04 12:00 | 2026-04-26 | 2026-04-09 12:00 | 2026-04-29 | 2026-04-19 12:00 | 2026-05-03 | 2026-05-04
|  | CLAER | CLAER | CLAER | - | - | U/SEWING | U/SEWING
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1