## MASTER (2)
GUESS KIDS MAINFALL - 6B | [14 empty] | FABRIC | [8 empty] | SIZE SET | [5 empty] | CUTTING |  |  |  |  | VAP-1 | [7 empty] | VAP-2 |  |  |  |  | VAP-3 |  |  |  |  | FEEDING |  |  |  |  | LINE PLAN sewing
SN |  |  | IMAGE | STYLE | FABRIC | COLOR |  | ORDER QTY | PRODUTION QTY | % | TOTAL QTY | PO DATE | DEL DATE | LEAD TIME | PROGRAM PASS | LOT CUTTING | COMMITMENT PLAN | ACUTAL PLAN | LEAD TIME | REQ QTY | REC DATE | REC QTY | STATUS | PROCESS | PP MEETING | PLAN | ACUTAL | LEAD TIME | STATUS | PLAN | ACUTAL | LEAD TIME | QTY | STATUS | SUPPLIER | PLAN | ACTAL SEND | CMOIT | REC DATE | QTY | LEAD TIME | STATUS | SUPPLIER | PLAN | ACUTAL | LEAD TIME | STATUS | SUPPLIER | PLAN | ACUTAL | LEAD TIME | STATUS | PLAN | ACUTAL | LEAD TIME | STATUS | REMAING DAYS | SUPPLIER | START | END | ACUTAL | STATUS
1 | 1126 | UNIT 2 |  | J6BG04 | FABRIC CODE-KQ63/ KN233460 - ECO COTTON SCUBA 360 -82% Organic COTTON, 16% POLYESTER, 2%Regular ELASTANE/SPANDEX | G7P1-19-3921 TCX BLACKENED BLUE |  | 1460 | 1549 | 106.1% | 1886 | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 |  | 2026-04-04 |  | 37 | 1065 |  |  |  | SIZE SET |  | 2026-04-09 |  | 5 |  | 2026-04-15 |  | 6 |  |  | VPR | 2026-04-26 |  |  |  |  | 46138 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-30 |  |  |  | -14 |  | 2026-04-24 | 2026-05-06
[6 empty] | G012-11-0605 TCX CREAM WHITE |  | 250 | 307 | 122.8% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 |  | 2026-04-04 |  | 37 | 333 |  |  |  | SHRINKAGE |  | 2026-04-09 |  | 5 |  | 2026-04-15 |  | 6 |  |  | VPR | 2026-04-26 |  |  |  |  | 46138 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-30 |  |  |  | -14 |  | 2026-04-24 | 2026-05-06
| 1150 |  |  |  |  | G7P1-19-3921 TCX BLACKENED BLUE |  | 99 | 140 | 141.4% |  | 2026-03-07 | 2026-05-28 | 82 | 2026-03-12 |  | 2026-04-04 |  | 23 | 80 |  |  |  | SHRINKAGE | [28 empty] | 1900-01-03 |  |  |  | -46166 |  | 2026-04-27 | 2026-05-06
[6 empty] | G012-11-0605 TCX CREAM WHITE |  | 77 | 118 | 153.2% |  | 2026-03-07 | 2026-05-28 | 82 | 2026-03-12 |  | 2026-04-04 |  | 23 | 68 |  |  |  | SHRINKAGE | [28 empty] | 1900-01-03 |  |  |  | -46166 |  | 2026-04-27 | 2026-05-06
2 | 1085 | UNIT 2 |  | J6BI02 | FABRIC CODE -J1314 / KN234780 - MID ORGANIC STRETCH JERSEY 180 50% Organic COTTON, 45% Regular COTTON, 5% Regular ELASTANE/SPANDEX | G011 |  | 2600 | 2738 | 105.3% | 7343 | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | STOCK | 2026-03-02 | 2026-03-14 | 4 | 473 |  | 473 | CLOSED | SIZE SET | 2026-03-14 | 2026-03-07 | 2026-03-17 | 5 | CLOSED | 2026-03-13 | 2026-03-19 | 6 | 2741 | CLOSED | FRESH | 2026-03-24 | 2026-03-23 | 2741 |  |  | 3 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-28 |  |  |  | -47 |  | 2026-03-30 | 2026-04-10
[6 empty] | G532 - 19-1557 TCX CHILLI RED |  | 250 | 323 | 129.2% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 |  | 2026-03-10 |  | 12 | 61 |  |  |  | SHRINKAGE | 2026-03-14 | 2026-03-15 |  | 5 |  | 2026-03-21 |  | 6 |  |  | FRESH | 2026-04-01 |  |  |  |  | 11 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-05 |  |  |  | -39 |  | 2026-03-30 | 2026-04-10
[6 empty] | G5B7-19-1652 TCX BEET JUICE RED |  | 1100 | 1162 | 105.6% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | 2026-03-19 | 2026-03-10 | 2026-03-28 | 12 | 201 | 2026-03-23 | 210 | CLOSED | SHRINKAGE | 2026-03-14 | 2026-03-15 |  | 5 |  | 2026-03-21 |  | 6 |  |  | FRESH | 2026-04-01 |  |  |  |  | 19 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-05 |  |  |  | -39 |  | 2026-03-30 | 2026-04-10
[6 empty] | JBLK |  | 3150 | 3306 | 105% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | STOCK | 2026-03-02 | 2026-03-13 | 4 | 571 | 3 | 571 | CLOSED | SHRINKAGE | 2026-03-14 | 2026-03-07 | 2026-03-17 | 5 | CLOSED | 2026-03-13 | 2026-03-19 | 6 | 3311 | CLOSED | FRESH | 2026-03-24 | 2026-03-23 | 3311 |  |  | 11 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-28 |  |  |  | -47 |  | 2026-03-30 | 2026-04-10
| 1153 |  |  |  |  | G011 |  | 243 | 285 | 117.3% |  | 2026-03-07 | 2026-05-28 | 82 | 2026-03-12 | STOCK | 2026-03-18 | 2026-03-14 | 6 | 50 |  | 50 | CLOSED | SHRINKAGE | 2026-03-14 | 2026-03-23 | 2026-03-18 | 5 | CLOSED | 2026-03-29 | 2026-03-24 | 6 | 288 | CLOSED | FRESH | 2026-04-09 |  |  |  |  | 19 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-13 |  |  |  | -45 |  | 2026-03-30 | 2026-04-10
3 | 1084 | UNIT 2 |  | J6BI10 | FABRIC CODE -J1314 / KN234780 - MID ORGANIC STRETCH JERSEY 180 50% Organic COTTON, 45% Regular COTTON, 5% Regular ELASTANE/SPANDEX | G011 |  | 300 | 364 | 121.3% | 1950 | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | STOCK | 2026-03-02 | 2026-03-13 | 4 | 61 |  | 61 | CLOSED | SHRINKAGE | 2026-03-14 | 2026-03-07 | 2026-03-16 | 5 | CLOSED | 2026-03-13 | 2026-03-18 | 6 | 367 | CLOSED | ESS.EMB | 2026-03-24 | 2026-03-20 | 367 |  |  | 3 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-28 |  |  |  | -47 |  | 2026-04-11 | 2026-04-16
[6 empty] | JBLK |  | 1650 | 1780 | 107.9% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | STANDARD | 2026-03-10 | 2026-03-13 | 12 | 288 |  | 307 | CLOSED | SHRINKAGE | 2026-03-14 | 2026-03-15 | 2026-03-16 | 5 | CLOSED | 2026-03-21 | 2026-03-19 | 6 | 1780 | CLOSED | ESS.EMB | 2026-04-03 | 2026-03-20 | 1780 |  |  | 1 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-07 |  |  |  | -37 |  | 2026-04-11 | 2026-04-16
4 | 1086 | UNIT 2 |  | J6BQ07 | FABRIC-KAV34/KN235535 -MID ORG. CO BRUSH FLEECE 340 KAV34 50% Regular COTTON,50% OrganicCOTTON | G5B7-19-1652 TCX BEET JUICE RED |  | 2000 | 2169 | 108.5% | 6000 | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 |  | 2026-03-22 |  | 24 | 914 |  |  |  | SHRINKAGE |  | 2026-03-27 |  | 5 |  | 2026-04-02 |  | 6 |  |  | FRESH | 2026-04-13 |  |  |  |  | 11 |  | VPR |  | 2026-04-24 | 11 |  | ESS.EMB | 2026-05-02 |  | 8 |  | 2026-05-06 |  |  |  | -8 |  | 2026-04-27 | 2026-05-15
[6 empty] | G012-11-0605 TCX CREAM WHITE |  | 1650 | 1788 | 108.4% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | PROJECTION | 2026-03-22 | 2026-03-19 | 24 | 588 |  |  |  | SHRINKAGE |  | 2026-03-27 |  | 5 |  | 2026-04-02 |  | 6 |  |  | FRESH | 2026-04-15 |  |  |  |  | 13 |  | VPR |  | 2026-04-26 | 11 |  | ESS.EMB | 2026-05-04 |  | 8 |  | 2026-05-08 |  |  |  | -6 |  | 2026-04-27 | 2026-05-15
[6 empty] | JBLK |  | 1550 | 1681 | 108.5% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | 2026-03-18 | 2026-03-22 | PROJECTION | 24 | 552 | 2026-03-19 | 588 | CLOSED | SHRINKAGE |  | 2026-03-27 |  | 5 |  | 2026-04-02 |  | 6 |  |  | FRESH | 2026-04-17 |  |  |  |  | 15 |  | VPR |  | 2026-04-28 | 11 |  | ESS.EMB | 2026-05-06 |  | 8 |  | 2026-05-10 |  |  |  | -4 |  | 2026-04-27 | 2026-05-15
[6 empty] | A62H -13-2803 TCX ROMANTIC LILLAC |  | 800 | 877 | 109.6% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 |  | 2026-03-22 |  | 24 | 293 |  |  |  | SHRINKAGE |  | 2026-03-27 |  | 5 |  | 2026-04-02 |  | 6 |  |  | FRESH | 2026-04-13 |  |  |  |  | 21 |  | VPR |  | 2026-04-24 | 11 |  | ESS.EMB | 2026-05-02 |  | 8 |  | 2026-05-06 |  |  |  | -8 |  | 2026-04-27 | 2026-05-15
5 | 1087 | UNIT 1 |  | J6BQ20 | FABIC CODE -KAV34/KN235535 - MID ORG. CO BRUSH FLEECE 340 KAV34 50% Regular COTTON, 50% Organic COTTON | G532 - 19-1557 TCX CHILLI RED |  | 510 | 575 | 112.7% | 6020 | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 |  | 2026-03-12 |  | 14 | 240 |  |  |  | SHRINKAGE |  | 2026-03-17 |  | 5 |  | 2026-03-23 |  | 6 |  |  | FRESH | 2026-04-03 |  |  |  |  | 11 |  | VPR |  | 2026-04-14 | 11 |  | N/A | N/A | N/A | N/A | N/A | 2026-04-18 |  |  |  | -26 |  | 2026-04-25 | 2026-05-11
[6 empty] | G012-11-0605 TCX CREAM WHITE |  | 3500 | 3752 | 107.2% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | 2026-03-07 | 2026-03-12 | 2026-03-18 | 14 | 1540 |  | 1116 | CLOSED | SHRINKAGE |  | 2026-03-17 |  | 5 |  | 2026-03-23 |  | 6 |  |  | FRESH | 2026-04-05 |  |  |  |  | 13 |  | VPR |  | 2026-04-16 | 11 |  | N/A | N/A | N/A | N/A | N/A | 2026-04-20 |  |  |  | -24 |  | 2026-04-25 | 2026-05-11
[6 empty] | JBLK |  | 2010 | 2160 | 107.5% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | 2026-03-18 | 2026-03-12 | 2026-03-18 | 14 | 890 | 2026-03-19 | 890 | CLOSED | SHRINKAGE |  | 2026-03-17 |  | 5 |  | 2026-03-23 |  | 6 |  |  | FRESH | 2026-04-07 |  |  |  |  | 6 |  | VPR |  | 2026-04-18 | 11 |  | N/A | N/A | N/A | N/A | N/A | 2026-04-22 |  |  |  | -22 |  | 2026-04-25 | 2026-05-11
6 | 1088 | UNIT2 |  | K6BI01 | FABRIC CODE -J1314/KN234780 - MID ORGANIC STRETCH JERSEY 180 J1314 50% Organic COTTON, 45% Regular COTTON, 5% Regular ELASTANE/SPANDEX | A62H -13-2803 TCX ROMANTIC LILLAC |  | 200 | 275 | 137.5% | 1600 | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 |  | 2026-03-21 |  | 23 | 35 |  |  |  | SHRINKAGE | 2026-03-05 | 2026-03-26 |  | 5 |  | 2026-04-01 |  | 6 |  |  | NAVEEN PRINT | 2026-04-12 |  |  |  |  | 30 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-16 |  |  |  | -28 |  | 2026-04-28 | 2026-02-05
[6 empty] | G011 |  | 400 | 487 | 121.8% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | STANDARD | 2026-03-02 | 2026-03-13 | 4 | 51 |  | 51 | CLOSED | SHRINKAGE | 2026-03-05 | 2026-03-07 | 2026-03-15 | 5 | CLOSED | 2026-03-13 | 2026-03-18 | 6 | 496 | CLOSED | NAVEEN PRINT | 2026-03-24 | 2026-03-12 | 496 |  |  | 3 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-28 |  |  |  | -47 |  | 2026-04-28 | 2026-02-05
[6 empty] | G532 - 19-1557 TCX CHILLI RED |  | 350 | 434 | 124% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 |  | 2026-03-10 |  | 12 | 50 |  |  |  | SHRINKAGE | 2026-03-05 | 2026-03-15 |  | 5 |  | 2026-03-21 |  | 6 |  |  | NAVEEN PRINT | 2026-04-01 |  |  |  |  | 19 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-05 |  |  |  | -39 |  | 2026-04-28 | 2026-02-05
[6 empty] | JBLK |  | 650 | 737 | 113.4% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | STOCK | 2026-03-02 | 2026-03-02 | 4 | 76 |  | 76 | CLOSED | SHRINKAGE | 2026-03-05 | 2026-03-07 | 2026-03-05 | 5 | CLOSED | 2026-03-13 | 2026-03-09 | 6 | 747 | CLOSED | NAVEEN PRINT | 2026-03-24 | 2026-03-12 | 747 | 2026-03-23 | 747 | -8 | CLOSED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-28 |  |  |  | -47 |  | 2026-04-28 | 2026-02-05
7 | 1089 | UNIT2 |  | K6BI03 | FABRIC CODE -J1314/KN234780 - MID ORGANIC STRETCH JERSEY 180 J1314 50% Organic COTTON, 45% Regular COTTON, 5% Regular ELASTANE/SPANDEX | A62H -13-2803 TCX ROMANTIC LILLAC |  | 1600 | 1705 | 106.6% | 6581 | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 |  | 2026-03-21 |  | 23 | 207 |  |  |  | SHRINKAGE | 2026-03-05 | 2026-03-26 |  | 5 |  | 2026-04-01 |  | 6 |  |  | NAVEEN PRINT | 2026-04-13 |  |  |  |  | 31 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-17 |  |  |  | -27 |  | 2026-05-02 | 2026-05-13
[6 empty] | G011 |  | 3100 | 3256 | 105% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | STOCK | 2026-03-02 |  | 4 | 390 |  |  |  | SHRINKAGE | 2026-03-05 | 2026-03-07 |  | 5 |  | 2026-03-13 |  | 6 |  |  | NAVEEN PRINT | 2026-03-25 |  |  |  |  | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-29 |  |  |  | -46 |  | 2026-05-02 | 2026-05-13
[6 empty] | G532 - 19-1557 TCX CHILLI RED |  | 550 | 647 | 117.6% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 |  | 2026-03-14 |  | 16 | 85 |  |  |  | SHRINKAGE | 2026-03-05 | 2026-03-19 |  | 5 |  | 2026-03-25 |  | 6 |  |  | NAVEEN PRINT | 2026-04-06 |  |  |  |  | 24 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-10 |  |  |  | -34 |  | 2026-05-02 | 2026-05-13
[6 empty] | JBLK |  | 600 | 697 | 116.2% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | STOCK | 2026-03-02 | 2026-03-02 | 4 | 85 | 2026-03-04 | 85 | CLOSED | SHRINKAGE | 2026-03-05 | 2026-03-07 | 2026-03-05 | 5 | CLOSED | 2026-03-13 | 2026-03-10 | 6 | 680 | CLOSED | NAVEEN PRINT | 2026-03-25 | 2026-03-12 | 680 | 2026-03-23 | 680 | 4 | CLOSED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-29 |  |  |  | -46 |  | 2026-05-02 | 2026-05-13
[6 empty] | BEAT JUICE RED |  | 600 | 673 | 112.2% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | 2026-03-19 | 2026-03-10 | 2026-03-28 | 14 | 91 | 2026-03-23 | 91 | CLOSED | SHRINKAGE | 2026-03-05 | 2026-03-15 |  | 5 |  | 2026-03-21 |  | 6 |  |  | NAVEEN PRINT | 2026-04-02 |  |  |  |  | 8 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-06 |  |  |  | -38 |  | 2026-05-02 | 2026-05-13
| 1182 |  |  |  |  | G5B7-19-1652 TCX BEET JUICE RED |  | 131 | 207 | 158% |  | 2026-03-07 | 2026-05-28 | 82 | 2026-03-12 |  | 2026-03-28 |  | 16 | 35 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | NAVEEN PRINT | 2026-04-20 | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-24 |  |  |  | -34 |  | 2026-05-02 | 2026-05-13
8 | 1090 | UNIT 1 |  | L6BI05 | FABRIC CODE- I3Z14/KN234781 - MID ORGANIC STREAM JERSEY 180 I3Z14 50% Regular COTTON, 50% Organic COTTON | G7T2 -19-4029 TCX BLUE LILY |  | 540 | 580 | 107.4% | 2520 | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | 2026-03-18 | 2026-03-14 |  | 16 | 133 |  |  |  | SHRINKAGE |  | 2026-03-19 |  | 5 |  | 2026-03-25 |  | 6 |  |  | FRESH | 2026-04-05 |  |  |  |  | 11 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-09 |  |  |  | -35 |  | 2026-04-14 | 2026-04-21
[6 empty] | G7V2-19-3924 TCX -SMART BLUE |  | 1090 | 1160 | 106.4% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 |  | 2026-03-14 |  | 16 | 253 |  |  |  | SHRINKAGE |  | 2026-03-19 |  | 5 |  | 2026-03-25 |  | 6 |  |  | FRESH | 2026-04-05 |  |  |  |  | 11 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-09 |  |  |  | -35 |  | 2026-04-14 | 2026-04-21
[6 empty] | G011 |  | 890 | 940 | 105.6% |  | 2026-02-20 | 2026-05-14 | 83 | 2026-02-26 | 2026-03-19 | 2026-03-14 |  | 16 | 208 |  | 198 | CLOSED | SHRINKAGE |  | 2026-03-19 |  | 5 |  | 2026-03-25 |  | 6 |  |  | FRESH | 2026-04-05 |  |  |  |  | 11 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-09 |  |  |  | -35 |  | 2026-04-14 | 2026-04-21
[11 empty] | 33900 | [41 empty] | 1900-01-03 |  |  |  | 4
10 | 1138 | UNIT 2 |  | H4BJ06 | 50% Regular COTTON, 50% Organic COTTON 180 GSM | JBLK |  | 1500 | 1604 | 106.9% | 2100 | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-28 |  | 16 | 298 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | FRESH | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -35
[6 empty] | SMART BLUE |  | 250 | 304 | 121.6% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-28 |  | 16 | 75 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | FRESH | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -35
[6 empty] | PURE WHITE |  | 350 | 410 | 117.1% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-28 |  | 16 | 77 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | FRESH | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -35
11 | 1140 | UNIT 2 |  | H4BT01 | 50% Regular COTTON, 50% Organic COTTON 180 GSM | SMART BLUE |  | 350 | 446 | 127.4% | 750 | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-28 |  | 16 | 48 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | FRESH | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -35
[6 empty] | PURE WHITE |  | 400 | 498 | 124.5% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-28 |  | 16 | 54 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | FRESH | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -35
12 | 1142 | UNIT 2 |  | J4YG01 | TOP -50% ORGANIC COTTON 50% REGULAR COTTON, PANT-50% ORGANIC COTTON 45% REGULAR 5% ELASTAN-180 GSM | JET BLACK |  | 1200 | 1298 | 108.2% | 1200 | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-04-04 |  | 23 | 683 |  |  |  | SHRINKAGE |  | 2026-04-09 |  | 5 |  | 2026-04-15 |  | 6 |  |  | FRESH | 2026-04-30 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-10 |  |  |  | -28
13 | 1146 | UNIT 2 |  | J4YI49 | 50% Organic COTTON, 44% Regular 6% elastan COTTON 230 GSM | JBLK |  | 1300 | 1372 | 105.5% | 3200 | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-31 |  | 19 | 283 |  |  |  | SHRINKAGE |  | 2026-04-05 |  | 5 |  | 2026-04-11 |  | 6 |  |  | ESS TEE | 2026-04-26 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 |  |  |  | -32
[6 empty] | BALLAT PINK |  | 400 | 456 | 114% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-04-05 |  | 24 | 87 |  |  |  | SHRINKAGE |  | 2026-04-10 |  | 5 |  | 2026-04-16 |  | 6 |  |  | ESS TEE | 2026-05-01 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-11 |  |  |  | -27
[6 empty] | PURE WHITE |  | 1500 | 1582 | 105.5% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-31 |  | 19 | 246 |  |  |  | SHRINKAGE |  | 2026-04-05 |  | 5 |  | 2026-04-11 |  | 6 |  |  | ESS TEE | 2026-04-26 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 |  |  |  | -32
14 | 1155 | UNIT 1 |  | J6BI20 | J1314 / KN234780 - MID ORGANIC STRETCH JERSEY 180 50% Organic COTTON, 45% Regular COTTON, 5% Regular ELASTANE/SPANDEX | G011 | chiffan - 38 , stone -30 | 1700 | 1787 | 105.1% | 4000 | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 | STOCK | 2026-03-26 |  | 14 | 288 |  |  |  | SHRINKAGE |  | 2026-03-31 |  | 5 |  | 2026-04-06 |  | 6 |  |  | VPR | 2026-04-21 |  |  |  |  | 15 |  | BALAJI | 2026-04-11 |  |  |  | N/A | N/A | N/A | N/A | N/A | 2026-04-21 |  |  |  | -47
[6 empty] | G532 - 19-1557 TCX CHILLI RED | chifan- 21 , stone-16 | 1600 | 1680 | 105% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-26 |  | 14 | 270 |  |  |  | SHRINKAGE |  | 2026-03-31 |  | 5 |  | 2026-04-06 |  | 6 |  |  | FRESH | 2026-04-21 |  |  |  |  | 15 |  | VPR | 2026-04-11 |  |  |  | BALAJI | 2026-04-21 |  |  |  | 2026-05-01 |  |  |  | -37
[6 empty] | G7P1-19-3921 TCX BLACKENED BLUE | chiffan - 42 , embro-18 | 700 | 743 | 106.1% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-26 |  | 14 | 120 |  |  |  | SHRINKAGE |  | 2026-03-31 |  | 5 |  | 2026-04-06 |  | 6 |  |  | ESS TEE | 2026-04-21 |  |  |  |  | 15 |  | BALAJI | 2026-04-11 |  |  |  | N/A | N/A | N/A | N/A | N/A | 2026-04-21 |  |  |  | -47
15 | 1160 | UNIT 2 |  | J6BI21 | J1314 / KN234780 - MID ORGANIC STRETCH JERSEY 180 50% Organic COTTON, 45% Regular COTTON, 5% Regular ELASTANE/SPANDEX | G011 | sticker -9 | 1100 | 1178 | 107.1% | 2530 | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-04-10 |  | 29 | 226 |  |  |  | SHRINKAGE |  | 2026-04-15 |  | 5 |  | 2026-04-21 |  | 6 |  |  | SWETHA | 2026-05-06 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-16 |  |  |  | -22
[6 empty] | G532 - 19-1557 TCX CHILLI RED |  | 230 | 290 | 126.1% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-04-10 |  | 29 | 26 |  |  |  | SHRINKAGE |  | 2026-04-15 |  | 5 |  | 2026-04-21 |  | 6 |  |  | SWETHA | 2026-05-06 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-16 |  |  |  | -22
[6 empty] | G7P1-19-3921 TCX BLACKENED BLUE |  | 1200 | 1281 | 106.7% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-04-10 |  | 29 | 246 |  |  |  | SHRINKAGE |  | 2026-04-15 |  | 5 |  | 2026-04-21 |  | 6 |  |  | SWETHA | 2026-05-06 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-16 |  |  |  | -22
16 | 1161 | UNIT 2 |  | J6BI23 | J1314 / KN234780 - MID ORGANIC STRETCH JERSEY 180 50% Organic COTTON, 45% Regular COTTON, 5% Regular ELASTANE/SPANDEX | G011 |  | 700 | 741 | 105.9% | 700 | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 | STOCK | 2026-03-18 | 2026-03-19 | 6 | 140 |  | 130 | CLOSED | SIZE SET |  | 2026-03-23 |  | 5 |  | 2026-03-29 |  | 6 |  |  | ESS TEE | 2026-04-13 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-23 |  |  |  | -45
17 | 1172 | UNIT 2 |  | J6BI30 | J1314 / KN234780 - MID ORGANIC STRETCH JERSEY 180 50% Organic COTTON, 45% Regular COTTON, 5% Regular ELASTANE/SPANDEX | G011 | 65 | 2600 | 2729 | 105% | 5350 | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-04-10 |  | 29 | 504 |  |  |  | SHRINKAGE |  | 2026-04-15 |  | 5 |  | 2026-04-21 |  | 6 |  |  | GARMENT FASHION | 2026-05-06 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-16 |  |  |  | -36
[6 empty] | JBLK | 35 | 2200 | 2316 | 105.3% |  | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-04-10 |  | 29 | 430 |  |  |  | SHRINKAGE |  | 2026-04-15 |  | 5 |  | 2026-04-21 |  | 6 |  |  | VPR | 2026-05-06 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-16 |  |  |  | -36
[6 empty] | G60N | 35 | 550 | 595 | 108.2% |  | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-04-10 |  | 29 | 112 |  |  |  | SHRINKAGE |  | 2026-04-15 |  | 5 |  | 2026-04-21 |  | 6 |  |  | VPR | 2026-05-06 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-16 |  |  |  | -36
18 | 1169 | UNIT 2 |  | J6BI31 | KN234567 -ECO VI COMPACT STR RIB 350 93% ECOVERO -Regular - Green VISCOSE/RAYON, 7% RegularELASTANE/SPANDEX | G011 |  | 1220 | 1279 | 104.8% | 1620 | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-04-08 |  | 27 | 139 |  |  |  | SIZE SET |  | 2026-04-13 |  | 5 |  | 2026-04-19 |  | 6 |  |  | ESS TEE | 2026-05-04 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-14 |  |  |  | -38
[6 empty] | JBLK |  | 400 | 455 | 113.8% |  | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-04-08 |  | 27 | 381 |  |  |  | SHRINKAGE |  | 2026-04-13 |  | 5 |  | 2026-04-19 |  | 6 |  |  | ESS TEE | 2026-05-04 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-14 |  |  |  | -38
19 | 1173 | UNIT 2 |  | J6BI41 | I3Z14- 50% Regular COTTON, 50% Organic COTTON 180 GSM | JBLK |  | 500 | 576 | 115.2% | 500 | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-03-26 |  | 14 | 92 |  |  |  | SHRINKAGE |  | 2026-03-31 |  | 5 |  | 2026-04-06 |  | 6 |  |  | VPR | 2026-04-21 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-01 |  |  |  | -51
20 | 1176 | UNIT 2 |  | J6BI44 | I3Z14- 50% Regular COTTON, 50% Organic COTTON 180 GSM | G011 |  | 550 | 614 | 111.6% | 1250 | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-03-31 |  | 19 | 93 |  |  |  | SHRINKAGE |  | 2026-04-05 |  | 5 |  | 2026-04-11 |  | 6 |  |  | FRESH | 2026-04-26 |  |  |  |  | 15 |  | VPR | 2026-04-13 |  |  |  | N/A | N/A | N/A | N/A | N/A | 2026-04-25 |  |  |  | -57
[6 empty] | JBLK |  | 300 | 372 | 124% |  | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-03-31 |  | 19 | 58 |  |  |  | SHRINKAGE |  | 2026-04-05 |  | 5 |  | 2026-04-11 |  | 6 |  |  | FRESH | 2026-04-26 |  |  |  |  | 15 |  | VPR | 2026-04-13 |  |  |  | N/A | N/A | N/A | N/A | N/A | 2026-04-25 |  |  |  | -57
[6 empty] | G63C |  | 400 | 477 | 119.2% |  | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-03-31 |  | 19 | 72 |  |  |  | SHRINKAGE |  | 2026-04-05 |  | 5 |  | 2026-04-11 |  | 6 |  |  | FRESH | 2026-04-26 |  |  |  |  | 15 |  | VPR | 2026-04-13 |  |  |  | N/A | N/A | N/A | N/A | N/A | 2026-04-25 |  |  |  | -57
21 | 1180 | UNIT 2 |  | J6BQ12 | KN235535 - MID ORG. CO BRUSH FLEECE 340 KAV34 50% Regular COTTON, 50% Organic COTTON | G012-11-0605 TCX CREAM WHITE |  | 480 | 529 | 110.2% | 1430 | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 | PROJECTION | 2026-04-15 |  | 34 | 278 |  |  |  | SIZE SET |  | 2026-04-20 |  | 5 |  | 2026-04-26 |  | 6 |  |  | ESS TEE | 2026-05-11 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-21 |  |  |  | -31
[6 empty] | G7JZ-12-4108 TCX FROZEN LIGHT BLUE |  | 950 | 1004 | 105.7% |  | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-04-15 |  | 34 | 550 |  |  |  | SHRINKAGE |  | 2026-04-20 |  | 5 |  | 2026-04-26 |  | 6 |  |  | ESS TEE | 2026-05-11 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-21 |  |  |  | -31
22 | 1184 | UNIT 1 |  | K6BI16 | KN234780 - MID ORGANIC STRETCH JERSEY 180 J1314 50% Organic COTTON, 45% Regular COTTON, 5% Regular ELASTANE/SPANDEX | G011 | chiffan -23 | 300 | 381 | 127% | 300 | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-03-28 |  | 16 | 52 |  |  |  | SIZE SET |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | NAVEEN | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -49
23 | 1185 | UNIT 2 |  | K6BI18 | KN234780 - MID ORGANIC STRETCH JERSEY 180 J1314 50% Organic COTTON, 45% Regular COTTON, 5% Regular ELASTANE/SPANDEX | G011 |  | 400 | 505 | 126.2% | 1050 | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-04-10 |  | 29 | 69 |  |  |  | SIZE SET |  | 2026-04-15 |  | 5 |  | 2026-04-21 |  | 6 |  |  | JAI SAKTHI | 2026-05-06 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-16 |  |  |  | -36
[6 empty] | G60N |  | 400 | 508 | 127% |  | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-04-10 |  | 29 | 66 |  |  |  | SHRINKAGE |  | 2026-04-15 |  | 5 |  | 2026-04-21 |  | 6 |  |  | JAI SAKTHI | 2026-05-06 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-16 |  |  |  | -36
[6 empty] | G7JZ-12-4108 TCX FROZEN LIGHT BLUE |  | 250 | 350 | 140% |  | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-04-10 |  | 29 | 59 |  |  |  | SHRINKAGE |  | 2026-04-15 |  | 5 |  | 2026-04-21 |  | 6 |  |  | JAI SAKTHI | 2026-05-06 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-16 |  |  |  | -36
24 | 1187 | UNIT 1 |  | K6BQ05 | KN237895 - ORGCO/RECYPOLY BRUSHED FLEECE 290 KG99 62% Organic COTTON, 38% Recycled POLYESTER | G7P1-19-3921 TCX BLACKENED BLUE |  | 300 | 380 | 126.7% | 300 | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-04-20 |  | 39 | 90 |  |  |  | SIZE SET |  | 2026-04-25 |  | 5 |  | 2026-05-01 |  | 6 |  |  | ESS TEE | 2026-05-16 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-26 |  |  |  | -12
25 | 1168 | UNIT 2 |  | L4BI13 | 50% Regular COTTON, 50% Organic COTTON 180 GSM | SMART BLUE |  | 1000 | 1100 | 110% | 2000 | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-28 |  | 16 | 238 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | ESS TEE | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -35
[6 empty] | PURE WHITE |  | 1000 | 1101 | 110.1% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-28 |  | 16 | 239 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | ESS TEE | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -35
26 | 1170 | UNIT 2 |  | L5BI16 | 50% Regular COTTON, 50% Organic COTTON 210 GSM | JBLK |  | 550 | 596 | 108.4% | 1100 | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-31 |  | 19 | 134 |  |  |  | SHRINKAGE |  | 2026-04-05 |  | 5 |  | 2026-04-11 |  | 6 |  |  | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-23 |  |  |  | -45
[6 empty] | PURE WHITE |  | 550 | 596 | 108.4% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-21 |  | 9 | 134 |  |  |  | SHRINKAGE |  | 2026-03-26 |  | 5 |  | 2026-04-01 |  | 6 |  |  | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-13 |  |  |  | -55
27 | 1188 | UNIT 1 |  | L6BI07 | KN234781 - MID ORGANIC STREAM JERSEY 180 I3Z14 50% Regular COTTON, 50% Organic COTTON | G011 |  | 350 | 411 | 117.4% | 350 | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-28 |  | 16 | 75 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | FRESH | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -35
28 | 1192 | UNIT 2 |  | N4BI08 | 50% Regular COTTON, 50% Organic COTTON 180 GSM | SMART BLUE |  | 200 | 316 | 158% | 450 | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-28 |  | 16 | 38 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | ESS TEE | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -35
[6 empty] | PURE WHITE |  | 250 | 266 | 106.4% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-28 |  | 16 | 41 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | ESS TEE | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -35
29 | 1189 | UNIT 2 |  | N6BI10 | KN234781 - MID ORGANIC STREAM JERSEY 180 I3Z14 50% Regular COTTON, 50% Organic | G011 | fresh -94 | 901 | 996 | 110.5% | 1201 | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-26 |  | 14 | 140 |  |  |  | SHRINKAGE |  | 2026-03-31 |  | 5 |  | 2026-04-06 |  | 6 |  |  | FRESH | 2026-04-21 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-01 |  |  |  | -37
[6 empty] | G7V2-19-3924 TCX - SMART BLUE | embro-6 | 150 | 223 | 148.7% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-26 |  | 14 | 38 |  |  |  | SHRINKAGE |  | 2026-03-31 |  | 5 |  | 2026-04-06 |  | 6 |  |  | FRESH | 2026-04-21 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-01 |  |  |  | -37
[6 empty] | G7EH -17-4020 TCX PARISIAN ROOFBLUE |  | 150 | 227 | 151.3% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-26 |  | 14 | 36 |  |  |  | SHRINKAGE |  | 2026-03-31 |  | 5 |  | 2026-04-06 |  | 6 |  |  | FRESH | 2026-04-21 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-01 |  |  |  | -37
30 | 1186 | UNIT 1 |  | N6BI11 | KN234781 - MID ORGANIC STREAM JERSEY 180 I3Z14 50% Regular COTTON, 50% Organic | G7EH -17-4020 TCX PARISIAN ROOFBLUE |  | 1200 | 1291 | 107.6% | 1900 | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-28 |  | 16 | 157 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | NAVEEN | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -35
[6 empty] | G7V2 SMART BLUE |  | 700 | 787 | 112.4% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-28 |  | 16 | 99 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | NAVEEN | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -35
31 | 1183 | UNIT 1 |  | N6BI15 | KN234781 - MID ORGANIC STREAM JERSEY 180 I3Z14 50% Regular COTTON, 50% Organic | G369 - 16-1460 TCX BRIGHT MANGO | fresh- 80 | 250 | 328 | 131.2% | 550 | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-28 |  | 16 | 49 |  |  |  | SIZE SET |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | GARMENT FASHION | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -35
[6 empty] | JBLK |  | 300 | 340 | 113.3% |  | 2026-03-06 | 2026-06-07 | 93 | 2026-03-12 |  | 2026-03-28 |  | 16 | 52 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | GARMENT FASHION | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -35
32 | 1167 | UNIT 1 |  | N6BI16 | KN234781 - MID ORGANIC STREAM JERSEY 180 I3Z14 50% Regular COTTON, 50% Organic | G011 PURE WHITE | 63 | 1320 | 1419 | 107.5% | 1870 | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-03-28 |  | 16 | 165 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | GARMENT FASHION | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -49
[6 empty] | G369 - 16-1460 TCX BRIGHT MANGO |  | 200 | 279 | 139.5% |  | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-03-28 |  | 16 | 40 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | GARMENT FASHION | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -49
[6 empty] | JBLK |  | 350 | 432 | 123.4% |  | 2026-03-06 | 2026-06-21 | 107 | 2026-03-12 |  | 2026-03-28 |  | 16 | 53 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | GARMENT FASHION | 2026-04-23 |  |  |  |  | 15 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-03 |  |  |  | -49
33 | 1190 | UNIT 2 |  | N0BI22 | 50% Regular COTTON, 50% Organic COTTON 180 GSM | PURE WHITE |  | 300 | 385 | 128.3% | 300 | 2026-03-07 | 2026-06-07 | 92 | 2026-03-12 |  | 2026-03-28 |  | 16 | 61 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-20 |  |  |  | -48
34 | 1191 | UNIT 2 |  | N0BI26 | 50% Regular COTTON, 50% Organic COTTON 180 GSM | PURE WHITE |  | 350 | 441 | 126% | 350 | 2026-03-07 | 2026-06-07 | 92 | 2026-03-12 |  | 2026-03-28 |  | 16 | 56 |  |  |  | SHRINKAGE |  | 2026-04-02 |  | 5 |  | 2026-04-08 |  | 6 |  |  | N/A | N/A |  | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-20 |  |  |  | -48
36351
70251
Formulas:
PLAN = [COMMITMENT PLAN]+5
PLAN = [CUTTING]+11
CUTTING = [PLAN]+6
FEEDING = [PLAN]+4
FEEDING = [ACUTAL]+4
ACUTAL = [PLAN]+11