## 63309
Orders Plan
Date : | 2026-04-21 |  | Order receipt | 2026-04-15 |  | Order L/D | 83
Job No | 63309 |  | Ex-Fty date | 2026-07-07 |  | Pre-Prod L/D | 45.65
Quantity : | 4501 |  | Delivery date | 2026-07-17 |  | Prodn L/D | 37.35
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-04-21 20:20 | 2026-05-03 06:14 | 2026-04-21 20:20 | 2026-05-07 19:48 | 2026-04-26 09:54 | 2026-05-12 09:22 | 2026-05-13 18:14 | 2026-05-16 22:55 | 2026-05-21 12:29 | 2026-05-28 08:49 | 2026-05-23 19:16 | 2026-06-01 22:23 | 2026-05-30 15:36
| Action | IN PROCESS
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-04-16 19:49 | 2026-04-19 13:34 | 2026-04-19 13:34 | 2026-04-20 22:26 | 2026-04-26 09:54 | 2026-04-28 16:41 | 2026-05-06 21:53 | 2026-05-07 19:48 | 2026-05-20 14:34 | 2026-05-20 14:34 | 2026-05-22 21:21 | 2026-05-23 19:16
| Action | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-30 15:36 | 2026-06-02 15:36 | 2026-06-21 | 2026-06-07 15:36 | 2026-06-26 | 2026-06-12 15:36 | 2026-06-29 | 2026-06-22 15:36 | 2026-07-03 | 2026-07-04
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 63305
Orders Plan
Date : | 2026-04-21 |  | Order receipt | 2026-04-15 |  | Order L/D | 83
Job No | 63305 |  | Ex-Fty date | 2026-07-07 |  | Pre-Prod L/D | 45.65
Quantity : | 5103 |  | Delivery date | 2026-07-17 |  | Prodn L/D | 37.35
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-04-21 20:20 | 2026-05-03 06:14 | 2026-04-21 20:20 | 2026-05-07 19:48 | 2026-04-26 09:54 | 2026-05-12 09:22 | 2026-05-13 18:14 | 2026-05-16 22:55 | 2026-05-21 12:29 | 2026-05-28 08:49 | 2026-05-23 19:16 | 2026-06-01 22:23 | 2026-05-30 15:36
| Action | IN PROCESS
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-04-16 19:49 | 2026-04-19 13:34 | 2026-04-19 13:34 | 2026-04-20 22:26 | 2026-04-26 09:54 | 2026-04-28 16:41 | 2026-05-06 21:53 | 2026-05-07 19:48 | 2026-05-20 14:34 | 2026-05-20 14:34 | 2026-05-22 21:21 | 2026-05-23 19:16
| Action | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-30 15:36 | 2026-06-02 15:36 | 2026-06-21 | 2026-06-07 15:36 | 2026-06-26 | 2026-06-12 15:36 | 2026-06-29 | 2026-06-22 15:36 | 2026-07-03 | 2026-07-04
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 63306
Orders Plan
Date : | 2026-04-21 |  | Order receipt | 2026-04-15 |  | Order L/D | 83
Job No | 63306 |  | Ex-Fty date | 2026-07-07 |  | Pre-Prod L/D | 45.65
Quantity : | 12704 |  | Delivery date | 2026-07-17 |  | Prodn L/D | 37.35
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-04-21 20:20 | 2026-05-03 06:14 | 2026-04-21 20:20 | 2026-05-07 19:48 | 2026-04-26 09:54 | 2026-05-12 09:22 | 2026-05-13 18:14 | 2026-05-16 22:55 | 2026-05-21 12:29 | 2026-05-28 08:49 | 2026-05-23 19:16 | 2026-06-01 22:23 | 2026-05-30 15:36
| Action | IN PROCESS
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-04-16 19:49 | 2026-04-19 13:34 | 2026-04-19 13:34 | 2026-04-20 22:26 | 2026-04-26 09:54 | 2026-04-28 16:41 | 2026-05-06 21:53 | 2026-05-07 19:48 | 2026-05-20 14:34 | 2026-05-20 14:34 | 2026-05-22 21:21 | 2026-05-23 19:16
| Action | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-30 15:36 | 2026-06-02 15:36 | 2026-06-21 | 2026-06-07 15:36 | 2026-06-26 | 2026-06-12 15:36 | 2026-06-29 | 2026-06-22 15:36 | 2026-07-03 | 2026-07-04
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 63315
Orders Plan
Date : | 2026-04-21 |  | Order receipt | 2026-04-15 |  | Order L/D | 83
Job No | 63315 |  | Ex-Fty date | 2026-07-07 |  | Pre-Prod L/D | 45.65
Quantity : | 210306 |  | Delivery date | 2026-07-17 |  | Prodn L/D | 37.35
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-04-21 20:20 | 2026-05-03 06:14 | 2026-04-21 20:20 | 2026-05-07 19:48 | 2026-04-26 09:54 | 2026-05-12 09:22 | 2026-05-13 18:14 | 2026-05-16 22:55 | 2026-05-21 12:29 | 2026-05-28 08:49 | 2026-05-23 19:16 | 2026-06-01 22:23 | 2026-05-30 15:36
| Action | IN PROCESS
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-04-16 19:49 | 2026-04-19 13:34 | 2026-04-19 13:34 | 2026-04-20 22:26 | 2026-04-26 09:54 | 2026-04-28 16:41 | 2026-05-06 21:53 | 2026-05-07 19:48 | 2026-05-20 14:34 | 2026-05-20 14:34 | 2026-05-22 21:21 | 2026-05-23 19:16
| Action | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-30 15:36 | 2026-06-02 15:36 | 2026-06-21 | 2026-06-07 15:36 | 2026-06-26 | 2026-06-12 15:36 | 2026-06-29 | 2026-06-22 15:36 | 2026-07-03 | 2026-07-04
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 63308
Orders Plan
Date : | 2026-04-21 |  | Order receipt | 2026-04-15 |  | Order L/D | 83
Job No | 63308 |  | Ex-Fty date | 2026-07-07 |  | Pre-Prod L/D | 45.65
Quantity : | 6909 |  | Delivery date | 2026-07-17 |  | Prodn L/D | 37.35
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-04-21 20:20 | 2026-05-03 06:14 | 2026-04-21 20:20 | 2026-05-07 19:48 | 2026-04-26 09:54 | 2026-05-12 09:22 | 2026-05-13 18:14 | 2026-05-16 22:55 | 2026-05-21 12:29 | 2026-05-28 08:49 | 2026-05-23 19:16 | 2026-06-01 22:23 | 2026-05-30 15:36
| Action | IN PROCESS
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-04-16 19:49 | 2026-04-19 13:34 | 2026-04-19 13:34 | 2026-04-20 22:26 | 2026-04-26 09:54 | 2026-04-28 16:41 | 2026-05-06 21:53 | 2026-05-07 19:48 | 2026-05-20 14:34 | 2026-05-20 14:34 | 2026-05-22 21:21 | 2026-05-23 19:16
| Action | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-30 15:36 | 2026-06-02 15:36 | 2026-06-21 | 2026-06-07 15:36 | 2026-06-26 | 2026-06-12 15:36 | 2026-06-29 | 2026-06-22 15:36 | 2026-07-03 | 2026-07-04
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1