## 62329
Orders Plan
Date : | 2026-04-17 |  | Order receipt | 2026-01-31 |  | Order L/D | 65
Job No | 62329 |  | Ex-Fty date | 2026-04-06 |  | Pre-Prod L/D | 35.75
Quantity : | 38670 |  | Delivery date | 2026-04-16 |  | Prodn L/D | 29.25
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-02-05 08:42 | 2026-02-14 07:12 | 2026-02-05 08:42 | 2026-02-17 21:00 | 2026-02-08 22:30 | 2026-02-21 10:48 | 2026-02-22 12:32 | 2026-02-25 00:36 | 2026-02-28 14:24 | 2026-03-05 23:06 | 2026-03-02 09:18 | 2026-03-09 12:54 | 2026-03-07 18:00
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
Deviation if any
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-02-01 10:19 | 2026-02-03 13:48 | 2026-02-03 13:48 | 2026-02-04 15:32 | 2026-02-08 22:30 | 2026-02-10 17:24 | 2026-02-17 03:50 | 2026-02-17 21:00 | 2026-02-27 21:14 | 2026-02-27 21:14 | 2026-03-01 16:08 | 2026-03-02 09:18
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-07 18:00 | 2026-03-10 18:00 | 2026-03-21 | 2026-03-15 18:00 | 2026-03-26 | 2026-03-20 18:00 | 2026-03-29 | 2026-03-30 18:00 | 2026-04-02 | 2026-04-03
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing | U/packing
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 62330
Orders Plan
Date : | 2026-04-17 |  | Order receipt | 2026-01-31 |  | Order L/D | 126
Job No | 62330 |  | Ex-Fty date | 2026-06-06 |  | Pre-Prod L/D | 69.3
Quantity : | 14700 |  | Delivery date | 2026-06-17 |  | Prodn L/D | 56.7
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-02-10 09:29 | 2026-02-27 17:17 | 2026-02-10 09:29 | 2026-03-06 15:36 | 2026-02-17 07:48 | 2026-03-13 13:55 | 2026-03-15 15:49 | 2026-03-20 12:14 | 2026-03-27 10:34 | 2026-04-06 20:02 | 2026-03-30 21:43 | 2026-04-13 18:22 | 2026-04-10 07:12
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-02-02 18:32 | 2026-02-06 22:19 | 2026-02-06 22:19 | 2026-02-09 00:13 | 2026-02-17 07:48 | 2026-02-20 18:58 | 2026-03-05 06:20 | 2026-03-06 15:36 | 2026-03-26 01:18 | 2026-03-26 01:18 | 2026-03-29 12:27 | 2026-03-30 21:43
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-10 07:12 | 2026-04-13 07:12 | 2026-05-21 | 2026-04-18 07:12 | 2026-05-26 | 2026-04-23 07:12 | 2026-05-29 | 2026-05-03 07:12 | 2026-06-02 | 2026-06-03
| Clear | Clear | U/CUTTING | U/CUTTING | NILL | NILL | U/sewing | U/sewing
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 62338
Orders Plan
Date : | 2026-04-17 |  | Order receipt | 2026-01-23 |  | Order L/D | 73
Job No | 62338 |  | Ex-Fty date | 2026-04-06 |  | Pre-Prod L/D | 40.15
Quantity : | 21204 |  | Delivery date | 2026-04-16 |  | Prodn L/D | 32.85
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-01-29 00:32 | 2026-02-08 01:26 | 2026-01-29 00:32 | 2026-02-12 01:48 | 2026-02-02 00:54 | 2026-02-16 02:10 | 2026-02-17 07:04 | 2026-02-20 02:31 | 2026-02-24 02:53 | 2026-03-02 03:25 | 2026-02-26 03:04 | 2026-03-06 03:47 | 2026-03-04 03:36
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-01-24 14:33 | 2026-01-27 00:22 | 2026-01-27 00:22 | 2026-01-28 05:16 | 2026-02-02 00:54 | 2026-02-04 01:05 | 2026-02-11 06:32 | 2026-02-12 01:48 | 2026-02-23 07:36 | 2026-02-23 07:36 | 2026-02-25 07:47 | 2026-02-26 03:04
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-04 03:36 | 2026-03-07 03:36 | 2026-03-21 | 2026-03-12 03:36 | 2026-03-26 | 2026-03-17 03:36 | 2026-03-29 | 2026-03-27 03:36 | 2026-04-02 | 2026-04-03
| Clear | Clear | Clear | Clear | NILL | NILL | U/sewing | U/sewing
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 62328
Orders Plan
Date : | 2026-04-17 |  | Order receipt | 2026-01-22 |  | Order L/D | 107
Job No | 62328 |  | Ex-Fty date | 2026-05-09 |  | Pre-Prod L/D | 58.85
Quantity : | 7200 |  | Delivery date | 2026-05-19 |  | Prodn L/D | 48.15
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-01-30 19:52 | 2026-02-14 12:58 | 2026-01-30 19:52 | 2026-02-20 10:12 | 2026-02-05 17:06 | 2026-02-26 07:26 | 2026-02-28 01:49 | 2026-03-04 04:41 | 2026-03-10 01:55 | 2026-03-18 21:47 | 2026-03-13 00:32 | 2026-03-24 19:01 | 2026-03-21 20:24
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-01-24 08:30 | 2026-01-27 21:14 | 2026-01-27 21:14 | 2026-01-29 15:37 | 2026-02-05 17:06 | 2026-02-08 15:43 | 2026-02-19 05:57 | 2026-02-20 10:12 | 2026-03-08 21:40 | 2026-03-08 21:40 | 2026-03-11 20:18 | 2026-03-13 00:32
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-21 20:24 | 2026-03-24 20:24 | 2026-04-23 | 2026-03-29 20:24 | 2026-04-28 | 2026-04-03 20:24 | 2026-05-01 | 2026-04-13 20:24 | 2026-05-05 | 2026-05-06
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 62339
Orders Plan
Date : | 2026-04-17 |  | Order receipt | 2026-01-23 |  | Order L/D | 104
Job No | 62339 |  | Ex-Fty date | 2026-05-07 |  | Pre-Prod L/D | 57.2
Quantity : | 329124 |  | Delivery date | 2026-05-17 |  | Prodn L/D | 46.8
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-01-31 13:55 | 2026-02-14 21:07 | 2026-01-31 13:55 | 2026-02-20 14:24 | 2026-02-06 07:12 | 2026-02-26 07:41 | 2026-02-28 00:52 | 2026-03-04 00:58 | 2026-03-09 18:14 | 2026-03-18 08:10 | 2026-03-12 14:53 | 2026-03-24 01:26 | 2026-03-21 04:48
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-01-25 06:55 | 2026-01-28 17:17 | 2026-01-28 17:17 | 2026-01-30 10:28 | 2026-02-06 07:12 | 2026-02-09 03:50 | 2026-02-19 10:57 | 2026-02-20 14:24 | 2026-03-08 14:47 | 2026-03-08 14:47 | 2026-03-11 11:25 | 2026-03-12 14:53
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-21 04:48 | 2026-03-24 04:48 | 2026-04-21 | 2026-03-29 04:48 | 2026-04-26 | 2026-04-03 04:48 | 2026-04-29 | 2026-04-13 04:48 | 2026-05-03 | 2026-05-04
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing | Clear | Clear | U/INSP
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 62950
Orders Plan
Date : | 2026-04-17 |  | Order receipt | 2026-03-07 |  | Order L/D | 95
Job No | 62950 |  | Ex-Fty date | 2026-06-10 |  | Pre-Prod L/D | 52.25
Quantity : | 20000 |  | Delivery date | 2026-06-20 |  | Prodn L/D | 42.75
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-03-14 20:06 | 2026-03-27 21:36 | 2026-03-14 20:06 | 2026-04-02 03:00 | 2026-03-20 01:30 | 2026-04-07 08:24 | 2026-04-08 22:01 | 2026-04-12 13:48 | 2026-04-17 19:12 | 2026-04-25 15:18 | 2026-04-20 09:54 | 2026-04-30 20:42 | 2026-04-28 06:00
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-03-09 02:10 | 2026-03-12 05:24 | 2026-03-12 05:24 | 2026-03-13 19:01 | 2026-03-20 01:30 | 2026-03-22 16:12 | 2026-04-01 01:55 | 2026-04-02 03:00 | 2026-04-16 18:07 | 2026-04-16 18:07 | 2026-04-19 08:49 | 2026-04-20 09:54
| Action | Clear | Clear | Clear | Clear | Clear | Clear | U/KNITTING | U/DYEING
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-28 06:00 | 2026-05-01 06:00 | 2026-05-25 | 2026-05-06 06:00 | 2026-05-30 | 2026-05-11 06:00 | 2026-06-02 | 2026-05-21 06:00 | 2026-06-06 | 2026-06-07
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 62951
Orders Plan
Date : | 2026-04-17 |  | Order receipt | 2026-03-07 |  | Order L/D | 95
Job No | 62951 |  | Ex-Fty date | 2026-06-10 |  | Pre-Prod L/D | 52.25
Quantity : | 12000 |  | Delivery date | 2026-06-20 |  | Prodn L/D | 42.75
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-03-14 20:06 | 2026-03-27 21:36 | 2026-03-14 20:06 | 2026-04-02 03:00 | 2026-03-20 01:30 | 2026-04-07 08:24 | 2026-04-08 22:01 | 2026-04-12 13:48 | 2026-04-17 19:12 | 2026-04-25 15:18 | 2026-04-20 09:54 | 2026-04-30 20:42 | 2026-04-28 06:00
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-03-09 02:10 | 2026-03-12 05:24 | 2026-03-12 05:24 | 2026-03-13 19:01 | 2026-03-20 01:30 | 2026-03-22 16:12 | 2026-04-01 01:55 | 2026-04-02 03:00 | 2026-04-16 18:07 | 2026-04-16 18:07 | 2026-04-19 08:49 | 2026-04-20 09:54
| Action | Clear | Clear | Clear | Clear | Clear | Clear | U/KNITTING | U/DYEING
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-28 06:00 | 2026-05-01 06:00 | 2026-05-25 | 2026-05-06 06:00 | 2026-05-30 | 2026-05-11 06:00 | 2026-06-02 | 2026-05-21 06:00 | 2026-06-06 | 2026-06-07
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 62949
Orders Plan
Date : | 2026-04-17 |  | Order receipt | 2026-03-07 |  | Order L/D | 95
Job No | 62949 |  | Ex-Fty date | 2026-06-10 |  | Pre-Prod L/D | 52.25
Quantity : | 14400 |  | Delivery date | 2026-06-20 |  | Prodn L/D | 42.75
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-03-14 20:06 | 2026-03-27 21:36 | 2026-03-14 20:06 | 2026-04-02 03:00 | 2026-03-20 01:30 | 2026-04-07 08:24 | 2026-04-08 22:01 | 2026-04-12 13:48 | 2026-04-17 19:12 | 2026-04-25 15:18 | 2026-04-20 09:54 | 2026-04-30 20:42 | 2026-04-28 06:00
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-03-09 02:10 | 2026-03-12 05:24 | 2026-03-12 05:24 | 2026-03-13 19:01 | 2026-03-20 01:30 | 2026-03-22 16:12 | 2026-04-01 01:55 | 2026-04-02 03:00 | 2026-04-16 18:07 | 2026-04-16 18:07 | 2026-04-19 08:49 | 2026-04-20 09:54
| Action | Clear | Clear | Clear | Clear | Clear | Clear | U/KNITTING | U/DYEING
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-28 06:00 | 2026-05-01 06:00 | 2026-05-25 | 2026-05-06 06:00 | 2026-05-30 | 2026-05-11 06:00 | 2026-06-02 | 2026-05-21 06:00 | 2026-06-06 | 2026-06-07
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 62336
Orders Plan
Date : | 2026-04-17 |  | Order receipt | 2026-01-27 |  | Order L/D | 107
Job No | 62336 |  | Ex-Fty date | 2026-05-14 |  | Pre-Prod L/D | 58.85
Quantity : | 3722 |  | Delivery date | 2026-05-24 |  | Prodn L/D | 48.15
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-02-04 19:52 | 2026-02-19 12:58 | 2026-02-04 19:52 | 2026-02-25 10:12 | 2026-02-10 17:06 | 2026-03-03 07:26 | 2026-03-05 01:49 | 2026-03-09 04:41 | 2026-03-15 01:55 | 2026-03-23 21:47 | 2026-03-18 00:32 | 2026-03-29 19:01 | 2026-03-26 20:24
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-01-29 08:30 | 2026-02-01 21:14 | 2026-02-01 21:14 | 2026-02-03 15:37 | 2026-02-10 17:06 | 2026-02-13 15:43 | 2026-02-24 05:57 | 2026-02-25 10:12 | 2026-03-13 21:40 | 2026-03-13 21:40 | 2026-03-16 20:18 | 2026-03-18 00:32
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-26 20:24 | 2026-03-29 20:24 | 2026-04-28 | 2026-04-03 20:24 | 2026-05-03 | 2026-04-08 20:24 | 2026-05-06 | 2026-04-18 20:24 | 2026-05-10 | 2026-05-11
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 62265
Orders Plan
Date : | 2026-04-17 |  | Order receipt | 2026-01-19 |  | Order L/D | 107
Job No | 62265 |  | Ex-Fty date | 2026-05-06 |  | Pre-Prod L/D | 58.85
Quantity : | 2200 |  | Delivery date | 2026-05-16 |  | Prodn L/D | 48.15
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-01-27 19:52 | 2026-02-11 12:58 | 2026-01-27 19:52 | 2026-02-17 10:12 | 2026-02-02 17:06 | 2026-02-23 07:26 | 2026-02-25 01:49 | 2026-03-01 04:41 | 2026-03-07 01:55 | 2026-03-15 21:47 | 2026-03-10 00:32 | 2026-03-21 19:01 | 2026-03-18 20:24
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-01-21 08:30 | 2026-01-24 21:14 | 2026-01-24 21:14 | 2026-01-26 15:37 | 2026-02-02 17:06 | 2026-02-05 15:43 | 2026-02-16 05:57 | 2026-02-17 10:12 | 2026-03-05 21:40 | 2026-03-05 21:40 | 2026-03-08 20:18 | 2026-03-10 00:32
| Action | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-18 20:24 | 2026-03-21 20:24 | 2026-04-20 | 2026-03-26 20:24 | 2026-04-25 | 2026-03-31 20:24 | 2026-04-28 | 2026-04-10 20:24 | 2026-05-02 | 2026-05-03
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## Sheet11 (hidden)
S.NO | JOB NO | REMARKS
1 | 62329 | Under prossecing jobs for knitting,dyeing,cuting,sewing & inspection
2 | 62330
3 | 62338
4 | 62328
5 | 62339
6 | 62950
7 | 62951
8 | 62949
9 | 62336
10 | 62265
11 | 63315 | New jobs opening date- 16-04-206
12 | 63306
13 | 63305
14 | 63308
15 | 63309