## 62330
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-31 |  | Order L/D | 67
Job No | 62330 |  | Ex-Fty date | 2026-04-02 |  | Pre-Prod L/D | 36.85
Quantity : | 4800 |  | Delivery date | 2026-04-08 |  | Prodn L/D | 30.15
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-08 20:24 | 2026-03-11 20:24 | 2026-03-17 | 2026-03-16 20:24 | 2026-03-22 | 2026-03-21 20:24 | 2026-03-25 | 2026-03-31 20:24 | 2026-03-29 | 2026-03-30
| Clear | Clear | U/CUTTING | U/CUTTING | NILL | NILL | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62330.1
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-31 |  | Order L/D | 98
Job No | 62330.1 |  | Ex-Fty date | 2026-05-01 |  | Pre-Prod L/D | 53.9
Quantity : | 4800 |  | Delivery date | 2026-05-09 |  | Prodn L/D | 44.1
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-25 21:36 | 2026-03-28 21:36 | 2026-04-15 | 2026-04-02 21:36 | 2026-04-20 | 2026-04-07 21:36 | 2026-04-23 | 2026-04-17 21:36 | 2026-04-27 | 2026-04-28
| Clear | Clear | U/CUTTING | U/CUTTING | NILL | NILL | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62330.2
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-31 |  | Order L/D | 129
Job No | 62330.2 |  | Ex-Fty date | 2026-05-23 |  | Pre-Prod L/D | 70.95
Quantity : | 4800 |  | Delivery date | 2026-06-09 |  | Prodn L/D | 58.05
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-11 22:48 | 2026-04-14 22:48 | 2026-05-07 | 2026-04-19 22:48 | 2026-05-12 | 2026-04-24 22:48 | 2026-05-15 | 2026-05-04 22:48 | 2026-05-19 | 2026-05-20
| Clear | Clear | U/CUTTING | U/CUTTING | NILL | NILL | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62330.3
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-31 |  | Order L/D | 65
Job No | 62330.3 |  | Ex-Fty date | 2026-03-31 |  | Pre-Prod L/D | 35.75
Quantity : | 300 |  | Delivery date | 2026-04-06 |  | Prodn L/D | 29.25
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-07 18:00 | 2026-03-10 18:00 | 2026-03-15 | 2026-03-15 18:00 | 2026-03-20 | 2026-03-20 18:00 | 2026-03-23 | 2026-03-30 18:00 | 2026-03-27 | 2026-03-28
| Clear | Clear | U/CUTTING | U/CUTTING | NILL | NILL | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62338
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-23 |  | Order L/D | 73
Job No | 62338 |  | Ex-Fty date | 2026-03-31 |  | Pre-Prod L/D | 40.15
Quantity : | 9600 |  | Delivery date | 2026-04-06 |  | Prodn L/D | 32.85
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-04 03:36 | 2026-03-07 03:36 | 2026-03-15 | 2026-03-12 03:36 | 2026-03-20 | 2026-03-17 03:36 | 2026-03-23 | 2026-03-27 03:36 | 2026-03-27 | 2026-03-28
| Clear | Clear | Clear | Clear | NILL | NILL | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62338.1
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-23 |  | Order L/D | 104
Job No | 62338.1 |  | Ex-Fty date | 2026-04-29 |  | Pre-Prod L/D | 57.2
Quantity : | 9600 |  | Delivery date | 2026-05-07 |  | Prodn L/D | 46.8
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-21 04:48 | 2026-03-24 04:48 | 2026-04-13 | 2026-03-29 04:48 | 2026-04-18 | 2026-04-03 04:48 | 2026-04-21 | 2026-04-13 04:48 | 2026-04-25 | 2026-04-26
| Clear | Clear | Clear | Clear | NILL | NILL | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62338.2
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-23 |  | Order L/D | 135
Job No | 62338.2 |  | Ex-Fty date | 2026-05-22 |  | Pre-Prod L/D | 74.25
Quantity : | 2004 |  | Delivery date | 2026-06-07 |  | Prodn L/D | 60.75
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-07 06:00 | 2026-04-10 06:00 | 2026-05-06 | 2026-04-15 06:00 | 2026-05-11 | 2026-04-20 06:00 | 2026-05-14 | 2026-04-30 06:00 | 2026-05-18 | 2026-05-19
| Clear | Clear | Clear | Clear | NILL | NILL | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62328
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-22 |  | Order L/D | 164
Job No | 62328 |  | Ex-Fty date | 2026-06-19 |  | Pre-Prod L/D | 90.2
Quantity : | 7200 |  | Delivery date | 2026-07-05 |  | Prodn L/D | 73.8
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-22 04:48 | 2026-04-25 04:48 | 2026-06-03 | 2026-04-30 04:48 | 2026-06-08 | 2026-05-05 04:48 | 2026-06-11 | 2026-05-15 04:48 | 2026-06-15 | 2026-06-16
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62339.1
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-23 |  | Order L/D | 73
Job No | 62339.1 |  | Ex-Fty date | 2026-03-31 |  | Pre-Prod L/D | 40.15
Quantity : | 180768 |  | Delivery date | 2026-04-06 |  | Prodn L/D | 32.85
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-04 03:36 | 2026-03-07 03:36 | 2026-03-15 | 2026-03-12 03:36 | 2026-03-20 | 2026-03-17 03:36 | 2026-03-23 | 2026-03-27 03:36 | 2026-03-27 | 2026-03-28
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing | Clear | Clear | U/INSP
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62339.2
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-23 |  | Order L/D | 104
Job No | 62339.2 |  | Ex-Fty date | 2026-04-29 |  | Pre-Prod L/D | 57.2
Quantity : | 122424 |  | Delivery date | 2026-05-07 |  | Prodn L/D | 46.8
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-21 04:48 | 2026-03-24 04:48 | 2026-04-13 | 2026-03-29 04:48 | 2026-04-18 | 2026-04-03 04:48 | 2026-04-21 | 2026-04-13 04:48 | 2026-04-25 | 2026-04-26
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing | Clear | Clear | U/INSP
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62339.3
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-23 |  | Order L/D | 131
Job No | 62339.3 |  | Ex-Fty date | 2026-05-18 |  | Pre-Prod L/D | 72.05
Quantity : | 1824 |  | Delivery date | 2026-06-03 |  | Prodn L/D | 58.95
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-05 01:12 | 2026-04-08 01:12 | 2026-05-02 | 2026-04-13 01:12 | 2026-05-07 | 2026-04-18 01:12 | 2026-05-10 | 2026-04-28 01:12 | 2026-05-14 | 2026-05-15
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing | Clear | Clear | U/INSP
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62339.4
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-23 |  | Order L/D | 135
Job No | 62339.4 |  | Ex-Fty date | 2026-05-22 |  | Pre-Prod L/D | 74.25
Quantity : | 24108 |  | Delivery date | 2026-06-07 |  | Prodn L/D | 60.75
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-07 06:00 | 2026-04-10 06:00 | 2026-05-06 | 2026-04-15 06:00 | 2026-05-11 | 2026-04-20 06:00 | 2026-05-14 | 2026-04-30 06:00 | 2026-05-18 | 2026-05-19
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing | Clear | Clear | U/INSP
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62950
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-03-07 |  | Order L/D | 95
Job No | 62950 |  | Ex-Fty date | 2026-06-02 |  | Pre-Prod L/D | 52.25
Quantity : | 20000 |  | Delivery date | 2026-06-10 |  | Prodn L/D | 42.75
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-28 06:00 | 2026-05-01 06:00 | 2026-05-17 | 2026-05-06 06:00 | 2026-05-22 | 2026-05-11 06:00 | 2026-05-25 | 2026-05-21 06:00 | 2026-05-29 | 2026-05-30
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62951
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-03-07 |  | Order L/D | 95
Job No | 62951 |  | Ex-Fty date | 2026-06-02 |  | Pre-Prod L/D | 52.25
Quantity : | 12000 |  | Delivery date | 2026-06-10 |  | Prodn L/D | 42.75
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-28 06:00 | 2026-05-01 06:00 | 2026-05-17 | 2026-05-06 06:00 | 2026-05-22 | 2026-05-11 06:00 | 2026-05-25 | 2026-05-21 06:00 | 2026-05-29 | 2026-05-30
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62949
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-03-07 |  | Order L/D | 88
Job No | 62949 |  | Ex-Fty date | 2026-05-28 |  | Pre-Prod L/D | 48.4
Quantity : | 14400 |  | Delivery date | 2026-06-03 |  | Prodn L/D | 39.6
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-24 09:36 | 2026-04-27 09:36 | 2026-05-12 | 2026-05-02 09:36 | 2026-05-17 | 2026-05-07 09:36 | 2026-05-20 | 2026-05-17 09:36 | 2026-05-24 | 2026-05-25
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62336
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-27 |  | Order L/D | 71
Job No | 62336 |  | Ex-Fty date | 2026-04-02 |  | Pre-Prod L/D | 39.05
Quantity : | 3096 |  | Delivery date | 2026-04-08 |  | Prodn L/D | 31.95
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-07 01:12 | 2026-03-10 01:12 | 2026-03-17 | 2026-03-15 01:12 | 2026-03-22 | 2026-03-20 01:12 | 2026-03-25 | 2026-03-30 01:12 | 2026-03-29 | 2026-03-30
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62336.1
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-27 |  | Order L/D | 107
Job No | 62336.1 |  | Ex-Fty date | 2026-05-06 |  | Pre-Prod L/D | 58.85
Quantity : | 50 |  | Delivery date | 2026-05-14 |  | Prodn L/D | 48.15
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-26 20:24 | 2026-03-29 20:24 | 2026-04-20 | 2026-04-03 20:24 | 2026-04-25 | 2026-04-08 20:24 | 2026-04-28 | 2026-04-18 20:24 | 2026-05-02 | 2026-05-03
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62336.2
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-27 |  | Order L/D | 127
Job No | 62336.2 |  | Ex-Fty date | 2026-05-18 |  | Pre-Prod L/D | 69.85
Quantity : | 576 |  | Delivery date | 2026-06-03 |  | Prodn L/D | 57.15
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-06 20:24 | 2026-04-09 20:24 | 2026-05-02 | 2026-04-14 20:24 | 2026-05-07 | 2026-04-19 20:24 | 2026-05-10 | 2026-04-29 20:24 | 2026-05-14 | 2026-05-15
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 62265
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-19 |  | Order L/D | 107
Job No | 62265 |  | Ex-Fty date | 2026-04-28 |  | Pre-Prod L/D | 58.85
Quantity : | 9100 |  | Delivery date | 2026-05-06 |  | Prodn L/D | 48.15
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-18 20:24 | 2026-03-21 20:24 | 2026-04-12 | 2026-03-26 20:24 | 2026-04-17 | 2026-03-31 20:24 | 2026-04-20 | 2026-04-10 20:24 | 2026-04-24 | 2026-04-25
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63305
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-27 |  | Order L/D | 161
Job No | 63305 |  | Ex-Fty date | 2026-06-20 |  | Pre-Prod L/D | 88.55
Quantity : | 2401 |  | Delivery date | 2026-07-07 |  | Prodn L/D | 72.45
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-25 13:12 | 2026-04-28 13:12 | 2026-06-04 | 2026-05-03 13:12 | 2026-06-09 | 2026-05-08 13:12 | 2026-06-12 | 2026-05-18 13:12 | 2026-06-16 | 2026-06-17
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63305.1
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-27 |  | Order L/D | 222
Job No | 63305.1 |  | Ex-Fty date | 2026-08-21 |  | Pre-Prod L/D | 122.1
Quantity : | 2702 |  | Delivery date | 2026-09-06 |  | Prodn L/D | 99.9
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-29 02:24 | 2026-06-01 02:24 | 2026-08-05 | 2026-06-06 02:24 | 2026-08-10 | 2026-06-11 02:24 | 2026-08-13 | 2026-06-21 02:24 | 2026-08-17 | 2026-08-18
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63306
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-27 |  | Order L/D | 161
Job No | 63306 |  | Ex-Fty date | 2026-06-20 |  | Pre-Prod L/D | 88.55
Quantity : | 10003 |  | Delivery date | 2026-07-07 |  | Prodn L/D | 72.45
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-25 13:12 | 2026-04-28 13:12 | 2026-06-04 | 2026-05-03 13:12 | 2026-06-09 | 2026-05-08 13:12 | 2026-06-12 | 2026-05-18 13:12 | 2026-06-16 | 2026-06-17
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63306.1
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-27 |  | Order L/D | 192
Job No | 63306.1 |  | Ex-Fty date | 2026-07-22 |  | Pre-Prod L/D | 105.6
Quantity : | 300 |  | Delivery date | 2026-08-07 |  | Prodn L/D | 86.4
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-12 14:24 | 2026-05-15 14:24 | 2026-07-06 | 2026-05-20 14:24 | 2026-07-11 | 2026-05-25 14:24 | 2026-07-14 | 2026-06-04 14:24 | 2026-07-18 | 2026-07-19
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63306.2
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-27 |  | Order L/D | 222
Job No | 63306.2 |  | Ex-Fty date | 2026-08-21 |  | Pre-Prod L/D | 122.1
Quantity : | 2401 |  | Delivery date | 2026-09-06 |  | Prodn L/D | 99.9
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-29 02:24 | 2026-06-01 02:24 | 2026-08-05 | 2026-06-06 02:24 | 2026-08-10 | 2026-06-11 02:24 | 2026-08-13 | 2026-06-21 02:24 | 2026-08-17 | 2026-08-18
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63308
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-31 |  | Order L/D | 157
Job No | 63308 |  | Ex-Fty date | 2026-06-20 |  | Pre-Prod L/D | 86.35
Quantity : | 2702 |  | Delivery date | 2026-07-07 |  | Prodn L/D | 70.65
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-27 08:24 | 2026-04-30 08:24 | 2026-06-04 | 2026-05-05 08:24 | 2026-06-09 | 2026-05-10 08:24 | 2026-06-12 | 2026-05-20 08:24 | 2026-06-16 | 2026-06-17
| Clear | Clear | U/CUTTING | U/CUTTING | NILL | NILL | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63308.1
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-31 |  | Order L/D | 218
Job No | 63308.1 |  | Ex-Fty date | 2026-08-21 |  | Pre-Prod L/D | 119.9
Quantity : | 4207 |  | Delivery date | 2026-09-06 |  | Prodn L/D | 98.1
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-30 21:36 | 2026-06-02 21:36 | 2026-08-05 | 2026-06-07 21:36 | 2026-08-10 | 2026-06-12 21:36 | 2026-08-13 | 2026-06-22 21:36 | 2026-08-17 | 2026-08-18
| Clear | Clear | U/CUTTING | U/CUTTING | NILL | NILL | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63309
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-23 |  | Order L/D | 165
Job No | 63309 |  | Ex-Fty date | 2026-06-20 |  | Pre-Prod L/D | 90.75
Quantity : | 2401 |  | Delivery date | 2026-07-07 |  | Prodn L/D | 74.25
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-23 18:00 | 2026-04-26 18:00 | 2026-06-04 | 2026-05-01 18:00 | 2026-06-09 | 2026-05-06 18:00 | 2026-06-12 | 2026-05-16 18:00 | 2026-06-16 | 2026-06-17
| Clear | Clear | Clear | Clear | NILL | NILL | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63309.1
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-23 |  | Order L/D | 196
Job No | 63309.1 |  | Ex-Fty date | 2026-07-22 |  | Pre-Prod L/D | 107.8
Quantity : | 2100 |  | Delivery date | 2026-08-07 |  | Prodn L/D | 88.2
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-10 19:12 | 2026-05-13 19:12 | 2026-07-06 | 2026-05-18 19:12 | 2026-07-11 | 2026-05-23 19:12 | 2026-07-14 | 2026-06-02 19:12 | 2026-07-18 | 2026-07-19
| Clear | Clear | Clear | Clear | NILL | NILL | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63315
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-27 |  | Order L/D | 131
Job No | 63315 |  | Ex-Fty date | 2026-05-22 |  | Pre-Prod L/D | 72.05
Quantity : | 6012 |  | Delivery date | 2026-06-07 |  | Prodn L/D | 58.95
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-09 01:12 | 2026-04-12 01:12 | 2026-05-06 | 2026-04-17 01:12 | 2026-05-11 | 2026-04-22 01:12 | 2026-05-14 | 2026-05-02 01:12 | 2026-05-18 | 2026-05-19
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63315.1
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-27 |  | Order L/D | 161
Job No | 63315.1 |  | Ex-Fty date | 2026-06-20 |  | Pre-Prod L/D | 88.55
Quantity : | 104203 |  | Delivery date | 2026-07-07 |  | Prodn L/D | 72.45
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-04-25 13:12 | 2026-04-28 13:12 | 2026-06-04 | 2026-05-03 13:12 | 2026-06-09 | 2026-05-08 13:12 | 2026-06-12 | 2026-05-18 13:12 | 2026-06-16 | 2026-06-17
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63315.2
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-27 |  | Order L/D | 192
Job No | 63315.2 |  | Ex-Fty date | 2026-07-22 |  | Pre-Prod L/D | 105.6
Quantity : | 35620 |  | Delivery date | 2026-08-07 |  | Prodn L/D | 86.4
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-12 14:24 | 2026-05-15 14:24 | 2026-07-06 | 2026-05-20 14:24 | 2026-07-11 | 2026-05-25 14:24 | 2026-07-14 | 2026-06-04 14:24 | 2026-07-18 | 2026-07-19
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63315.3
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-27 |  | Order L/D | 222
Job No | 63315.3 |  | Ex-Fty date | 2026-08-21 |  | Pre-Prod L/D | 122.1
Quantity : | 26824 |  | Delivery date | 2026-09-06 |  | Prodn L/D | 99.9
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-29 02:24 | 2026-06-01 02:24 | 2026-08-05 | 2026-06-06 02:24 | 2026-08-10 | 2026-06-11 02:24 | 2026-08-13 | 2026-06-21 02:24 | 2026-08-17 | 2026-08-18
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63315.4
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-27 |  | Order L/D | 202
Job No | 63315.4 |  | Ex-Fty date | 2026-07-31 |  | Pre-Prod L/D | 111.1
Quantity : | 1260 |  | Delivery date | 2026-08-17 |  | Prodn L/D | 90.9
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-18 02:24 | 2026-05-21 02:24 | 2026-07-15 | 2026-05-26 02:24 | 2026-07-20 | 2026-05-31 02:24 | 2026-07-23 | 2026-06-10 02:24 | 2026-07-27 | 2026-07-28
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63315.5
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-27 |  | Order L/D | 232
Job No | 63315.5 |  | Ex-Fty date | 2026-08-31 |  | Pre-Prod L/D | 127.6
Quantity : | 900 |  | Delivery date | 2026-09-16 |  | Prodn L/D | 104.4
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-06-03 14:24 | 2026-06-06 14:24 | 2026-08-15 | 2026-06-11 14:24 | 2026-08-20 | 2026-06-16 14:24 | 2026-08-23 | 2026-06-26 14:24 | 2026-08-27 | 2026-08-28
| Clear | Clear | Clear | Clear | Clear | Clear | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## 63261
Orders Plan
Date : | 2026-04-30 |  | Order receipt | 2026-01-23 |  | Order L/D | 104
Job No | 63261 |  | Ex-Fty date | 2026-04-29 |  | Pre-Prod L/D | 57.2
Quantity : | 16200 |  | Delivery date | 2026-05-07 |  | Prodn L/D | 46.8
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-03-21 04:48 | 2026-03-24 04:48 | 2026-04-13 | 2026-03-29 04:48 | 2026-04-18 | 2026-04-03 04:48 | 2026-04-21 | 2026-04-13 04:48 | 2026-04-25 | 2026-04-26
| Clear | Clear | Clear | Clear | NILL | NILL | U/sewing | U/sewing
Formulas:
Cutting start = [PCD]+3
Cutting complete = [Prnt/Emb Complete]-5
Prnt/Emb Start = [Cutting start]+5
Prnt/Emb Complete = [Sewing Complete]-3
Sewing Start = [Prnt/Emb Start]+5
Sewing Complete = [CIP complete]-4
CIP start = [Sewing Start]+10
CIP complete = [Final Inspection]-1

## Sheet11 (hidden)
S.NO | JOB NO | REMARKS
1 | 62329 | Under prossecing jobs for knitting,dyeing,cuting,sewing & inspection
2 | 62330
3 | 62338
4 | 62328
5 | 62339
6 | 62950
7 | 62951
8 | 62949
9 | 62336
10 | 62265
11 | 63315 | New jobs opening date- 16-04-206
12 | 63306
13 | 63305
14 | 63308
15 | 63309