## 63315
Orders Plan
Date : | 2026-04-17 |  | Order receipt | 2026-04-16 |  | Order L/D | 52
Job No | 63315 |  | Ex-Fty date | 2026-06-07 |  | Pre-Prod L/D | 28.6
Quantity : | 254886 |  | Delivery date | 2026-06-17 |  | Prodn L/D | 23.4
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-04-20 06:58 | 2026-04-27 10:34 | 2026-04-20 06:58 | 2026-04-30 07:12 | 2026-04-23 03:36 | 2026-05-03 03:50 | 2026-05-04 00:26 | 2026-05-06 00:29 | 2026-05-08 21:07 | 2026-05-13 04:05 | 2026-05-10 07:26 | 2026-05-16 00:43 | 2026-05-14 14:24
Action
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-04-17 03:27 | 2026-04-18 20:38 | 2026-04-18 20:38 | 2026-04-19 17:14 | 2026-04-23 03:36 | 2026-04-24 13:55 | 2026-04-29 17:28 | 2026-04-30 07:12 | 2026-05-08 07:24 | 2026-05-08 07:24 | 2026-05-09 17:43 | 2026-05-10 07:26
| Action | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-14 14:24 | 2026-05-17 14:24 | 2026-05-22 | 2026-05-22 14:24 | 2026-05-27 | 2026-05-27 14:24 | 2026-05-30 | 2026-06-06 14:24 | 2026-06-03 | 2026-06-04
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 63306
Orders Plan
Date : | 2026-04-17 |  | Order receipt | 2026-04-16 |  | Order L/D | 113
Job No | 63306 |  | Ex-Fty date | 2026-08-07 |  | Pre-Prod L/D | 62.15
Quantity : | 12704 |  | Delivery date | 2026-08-17 |  | Prodn L/D | 50.85
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-04-25 07:44 | 2026-05-10 20:38 | 2026-04-25 07:44 | 2026-05-17 01:48 | 2026-05-01 12:54 | 2026-05-23 06:58 | 2026-05-25 03:42 | 2026-05-29 12:07 | 2026-06-04 17:17 | 2026-06-14 01:01 | 2026-06-07 19:52 | 2026-06-20 06:11 | 2026-06-17 03:36
Action
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-04-18 11:40 | 2026-04-22 05:10 | 2026-04-22 05:10 | 2026-04-24 01:54 | 2026-05-01 12:54 | 2026-05-04 15:29 | 2026-05-15 19:58 | 2026-05-17 01:48 | 2026-06-03 11:27 | 2026-06-03 11:27 | 2026-06-06 14:02 | 2026-06-07 19:52
| Action | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-06-17 03:36 | 2026-06-20 03:36 | 2026-07-22 | 2026-06-25 03:36 | 2026-07-27 | 2026-06-30 03:36 | 2026-07-30 | 2026-07-10 03:36 | 2026-08-03 | 2026-08-04
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 63305
Orders Plan
Date : | 2026-04-17 |  | Order receipt | 2026-04-16 |  | Order L/D | 82
Job No | 63305 |  | Ex-Fty date | 2026-07-07 |  | Pre-Prod L/D | 45.1
Quantity : | 5103 |  | Delivery date | 2026-07-17 |  | Prodn L/D | 36.9
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-04-22 18:22 | 2026-05-04 00:58 | 2026-04-22 18:22 | 2026-05-08 13:12 | 2026-04-27 06:36 | 2026-05-13 01:26 | 2026-05-14 09:55 | 2026-05-17 13:41 | 2026-05-22 01:55 | 2026-05-28 20:17 | 2026-05-24 08:02 | 2026-06-02 08:31 | 2026-05-31 02:24
Action
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-04-17 19:18 | 2026-04-20 12:14 | 2026-04-20 12:14 | 2026-04-21 20:43 | 2026-04-27 06:36 | 2026-04-29 12:43 | 2026-05-07 15:33 | 2026-05-08 13:12 | 2026-05-21 04:16 | 2026-05-21 04:16 | 2026-05-23 10:24 | 2026-05-24 08:02
| Action | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-31 02:24 | 2026-06-03 02:24 | 2026-06-21 | 2026-06-08 02:24 | 2026-06-26 | 2026-06-13 02:24 | 2026-06-29 | 2026-06-23 02:24 | 2026-07-03 | 2026-07-04
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 63308
Orders Plan
Date : | 2026-04-17 |  | Order receipt | 2026-04-16 |  | Order L/D | 82
Job No | 63308 |  | Ex-Fty date | 2026-07-07 |  | Pre-Prod L/D | 45.1
Quantity : | 4207 |  | Delivery date | 2026-07-17 |  | Prodn L/D | 36.9
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-04-22 18:22 | 2026-05-04 00:58 | 2026-04-22 18:22 | 2026-05-08 13:12 | 2026-04-27 06:36 | 2026-05-13 01:26 | 2026-05-14 09:55 | 2026-05-17 13:41 | 2026-05-22 01:55 | 2026-05-28 20:17 | 2026-05-24 08:02 | 2026-06-02 08:31 | 2026-05-31 02:24
Action
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-04-17 19:18 | 2026-04-20 12:14 | 2026-04-20 12:14 | 2026-04-21 20:43 | 2026-04-27 06:36 | 2026-04-29 12:43 | 2026-05-07 15:33 | 2026-05-08 13:12 | 2026-05-21 04:16 | 2026-05-21 04:16 | 2026-05-23 10:24 | 2026-05-24 08:02
| Action | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-31 02:24 | 2026-06-03 02:24 | 2026-06-21 | 2026-06-08 02:24 | 2026-06-26 | 2026-06-13 02:24 | 2026-06-29 | 2026-06-23 02:24 | 2026-07-03 | 2026-07-04
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1

## 63309
Orders Plan
Date : | 2026-04-17 |  | Order receipt | 2026-04-16 |  | Order L/D | 82
Job No | 63309 |  | Ex-Fty date | 2026-07-07 |  | Pre-Prod L/D | 45.1
Quantity : | 4501 |  | Delivery date | 2026-07-17 |  | Prodn L/D | 36.9
Pre- Production TNA |  | L/D send | L/D appl | Fit send | Fit appl | A/W send | A/W appl | I/B Fab send | I/B fab appl | PP send | PP appl | FPT | GPT | PCD
| Plan | 2026-04-22 18:22 | 2026-05-04 00:58 | 2026-04-22 18:22 | 2026-05-08 13:12 | 2026-04-27 06:36 | 2026-05-13 01:26 | 2026-05-14 09:55 | 2026-05-17 13:41 | 2026-05-22 01:55 | 2026-05-28 20:17 | 2026-05-24 08:02 | 2026-06-02 08:31 | 2026-05-31 02:24
Action
| Deviation if any | .
Fabric TNA |  | Job sheet | Consumption Locking | Costing Freezed | Yarn Req. deadline | Yarn I/H | Knit start | Knit Complete | Dyeing start | Dyeing complete | Finishing start | finishing Complete | Fabric I/H
| Plan | 2026-04-17 19:18 | 2026-04-20 12:14 | 2026-04-20 12:14 | 2026-04-21 20:43 | 2026-04-27 06:36 | 2026-04-29 12:43 | 2026-05-07 15:33 | 2026-05-08 13:12 | 2026-05-21 04:16 | 2026-05-21 04:16 | 2026-05-23 10:24 | 2026-05-24 08:02
| Action | Clear
Deviation if any
Production TNA |  | PCD | Cutting start | Cutting complete | Prnt/Emb Start | Prnt/Emb Complete | Sewing Start | Sewing Complete | CIP start | CIP complete | Final Inspection
| Plan | 2026-05-31 02:24 | 2026-06-03 02:24 | 2026-06-21 | 2026-06-08 02:24 | 2026-06-26 | 2026-06-13 02:24 | 2026-06-29 | 2026-06-23 02:24 | 2026-07-03 | 2026-07-04
Formulas:
Fit send = [A/W send]-5
Fit appl = [L/D appl]+5
A/W send = [I/B Fab send]-3
A/W appl = [Fit appl]+5
I/B Fab send = [PP send]-4
I/B fab appl = [A/W appl]+10
PP send = [PP appl]-1